## Task Handover Tracker
ACTIVITY TASK HANDOVER TRACKER
Track task ownership, progress, and handover status across teams and activities | [7 empty] | Last Updated: March 17, 2026
TASK IDENTIFICATION |  |  |  | OWNERSHIP & ASSIGNMENT |  |  | TIMELINE |  |  | HANDOVER DETAILS |  |  | STATUS & PRIORITY
# | Activity / Project | Task Name | Description | Task Owner | Handing Over To | Department / Team | Start Date | Due Date | Handover Date | Handover Notes | Acceptance Criteria | Sign-Off By | Priority | Status | % Complete
1 | ERP Implementation | System Configuration | Configure GL and AP modules | Sarah Chen | Mike Patel | IT / Finance | 2026-02-01 | 2026-03-20 | 2026-03-15 | All config docs in SharePoint | Tested in UAT & approved by Finance | CFO | High | Completed | 100%
2 | ERP Implementation | Data Migration | Migrate historical data to new system | James Wright | Sarah Chen | IT | 2026-02-15 | 2026-04-01 | 2026-03-28 | Use migration runbook v3 | Zero data loss; reconcile record counts | IT Director | Critical | In Progress | 65%
3 | ERP Implementation | User Training | Conduct end-user training sessions | Emily Davis | HR Team | HR / Training | 2026-03-01 | 2026-04-15 | 2026-04-10 | Training deck shared via LMS | 80% completion rate on assessment | CHRO | High | Not Started | 0%
4 | Q2 Marketing Campaign | Campaign Planning | Define campaign goals and budget | Tom Nguyen | Lisa Park | Marketing | 2026-02-10 | 2026-03-10 | 2026-03-05 | Brief doc emailed to Lisa | Approved campaign brief signed | CMO | Medium | Completed | 100%
5 | Q2 Marketing Campaign | Creative Production | Design ads and copy assets | Lisa Park | Creative Agency | Marketing | 2026-03-05 | 2026-04-01 | 2026-03-25 | Brand guidelines in Dropbox | Final assets approved by brand team | CMO | High | In Progress | 40%
6 | Office Relocation | IT Infrastructure Setup | Set up network and workstations | Dev Kumar | Facilities Mgr | IT | 2026-03-10 | 2026-05-01 | 2026-04-28 | Network diagram v2 filed | All endpoints tested and live | CTO | Medium | Not Started | 0%
7 | Office Relocation | Vendor Coordination | Liaise with movers and fit-out vendors | Anna Smith | Dev Kumar | Operations | 2026-03-01 | 2026-04-20 | 2026-04-15 | Vendor contracts in legal drive | All contracts signed; schedule confirmed | COO | Low | In Progress | 55%
8 | Product Launch – v3.0 | QA Testing | Run full regression and UAT | Raj Mehta | PM Team | Engineering | 2026-02-20 | 2026-03-31 | 2026-03-28 | Test cases in Jira | Pass rate ≥ 98%; P1 bugs = 0 | CPO | Critical | In Progress | 80%
9 | Product Launch – v3.0 | Release Communication | Draft internal & external release notes | Sophie Turner | Marketing | Product | 2026-03-15 | 2026-04-05 | 2026-04-01 | Comms plan template shared | Approved by Legal and Product | CPO | Medium | Not Started | 0%
10 | Compliance Review | Policy Update | Update data privacy policies | Chris Brown | Legal Counsel | Legal / Compliance | 2026-01-15 | 2026-03-15 | 2026-03-10 | Redline docs in legal folder | Board sign-off obtained | General Counsel | Critical | Completed | 100%
TOTALS / SUMMARY | [12 empty] | 3 | 3 | N/A

## Dashboard
HANDOVER DASHBOARD – AT A GLANCE
TOTAL TASKS |  | COMPLETED |  | IN PROGRESS |  | NOT STARTED |  | CRITICAL TASKS | AVG COMPLETION
10 |  | 3 |  | 4 |  | 3 |  | 3 | 0
STATUS BREAKDOWN |  |  |  |  | PRIORITY BREAKDOWN
# | Status | Count | % of Total |  | # | Priority | Count | % of Total
1 | Completed | 3 | 30% |  | 1 | Critical | 3 | 30%
2 | In Progress | 4 | 40% |  | 2 | High | 3 | 30%
3 | Not Started | 3 | 30% |  | 3 | Medium | 3 | 30%
4 | On Hold | 0 | 0% |  | 4 | Low | 1 | 10%
💡 TIP: Use the filters in the Task Handover Tracker sheet to slice by Owner, Status, Priority, or Department.

## Instructions
HOW TO USE THIS TRACKER
STEP | ACTION | NOTES
1 | Open Task Handover Tracker sheet | This is the main data entry sheet
2 | Fill in Activity / Project | Group related tasks under one activity name
3 | Enter Task Name & Description | Be specific so the receiver understands scope
4 | Set Task Owner | The person currently responsible for the task
5 | Set Handing Over To | The person who will take over the task
6 | Enter Start, Due & Handover Dates | Use DD/MM/YYYY format
7 | Fill in Handover Notes | Document anything critical the receiver needs to know
8 | Define Acceptance Criteria | What does done look like for this handover?
9 | Set Priority (dropdown) | Critical / High / Medium / Low
10 | Update Status (dropdown) | Not Started / In Progress / On Hold / Completed
11 | Update % Complete | Enter as a percentage e.g. 75%
12 | View Dashboard | Check the Dashboard tab for live summary KPIs