Windows Server 2016 and SQL Server 2016 to 2022

In-Place Upgrade Procedure Manual

Document classification: Internal – Confidential
Document owner: Infrastructure Services / Database Services
Change type: High-risk production infrastructure change
Applicable environment: VMware-based Windows Server and SQL Server workloads in an enterprise financial-services environment
Template note: Replace all fields in square brackets before CAB submission and execution.

Important: A direct Windows Server 2016 to Windows Server 2022 in-place upgrade is supported for non-clustered systems. However, Windows Failover Cluster rolling upgrades progress only one OS release at a time, so clustered nodes require a different method and cannot use this direct two-version path.

Important: SQL Server 2016 can be upgraded directly to SQL Server 2022. Ensure that the target operating system, installed SQL features, editions, and application dependencies have been formally assessed first.

Warning: This is an execution template, not a substitute for vendor compatibility certification, approved change records, tested recovery procedures, or environment-specific runbooks. A production-like rehearsal is mandatory.

1.0 Document Control

| Field | Value |
| --- | --- |
| Document title | Windows Server 2016 and SQL Server 2016 to 2022 In-Place Upgrade Procedure Manual |
| Document ID | [SOP-INF-WS-SQL-UPG-001] |
| Version | 1.0 |
| Status | Draft / CAB Review / Approved / Retired |
| Owner | [Infrastructure Manager / Platform Owner] |
| Technical owners | [Windows SME], [SQL DBA Lead], [VMware Lead] |
| Business owner | [Application Owner] |
| Change record | [CHGxxxxxxxx] |
| Planned implementation date | [DD-MMM-YYYY] |
| Planned outage | [Start Date/Time] to [End Date/Time] |
| Environment | Production / DR / UAT / Test |
| Classification | Internal – Confidential |
| Review cycle | Annual and after material platform change |

1.1 Version History

| Version | Date | Author | Reviewer | Description |
| --- | --- | --- | --- | --- |
| 0.1 | [DD-MMM-YYYY] | [Name] | [Name] | Initial draft |
| 0.9 | [DD-MMM-YYYY] | [Name] | [Name] | CAB-ready revision |
| 1.0 | [DD-MMM-YYYY] | [Name] | [Name] | Approved production procedure |

1.2 Approvals

| Role | Name | Signature / Approval Reference | Date |
| --- | --- | --- | --- |
| Application owner | [Name] | [Reference] | [Date] |
| Infrastructure owner | [Name] | [Reference] | [Date] |
| DBA lead | [Name] | [Reference] | [Date] |
| Information security | [Name] | [Reference] | [Date] |
| Backup/DR owner | [Name] | [Reference] | [Date] |
| Change manager | [Name] | [Reference] | [Date] |
| CAB | [Name/Record] | [Reference] | [Date] |

2.0 Purpose

This SOP defines the controlled, auditable process to upgrade:

- Windows Server 2016 to Windows Server 2022 in place.

- SQL Server 2016 to SQL Server 2022 in place.

- Supporting server components, agents, monitoring, backup, security tooling, and operational controls.

The procedure is designed to preserve system configuration, installed roles, applications, and data where supported, while ensuring a verified rollback route. Microsoft describes an in-place OS upgrade as retaining settings, roles, features, and data, subject to role and configuration compatibility.

3.0 Scope

3.1 In Scope

- VMware virtual machines running Windows Server 2016.

- SQL Server 2016 standalone instances.

- SQL Server 2016 instances participating in supported high-availability designs, subject to separate topology-specific approval.

- SQL Server Database Engine and installed components such as Agent, SSIS, SSAS, SSRS, replication, and Full-Text Search where validated.

- Monitoring integrations: SCOM, SolarWinds, Splunk, Instana, Prometheus, or equivalent.

- Enterprise backup, AV/EDR, vulnerability scanning, privileged-access, and log-forwarding agents.

- Production, DR, UAT, and non-production environments.

3.2 Out of Scope

- Unsupported Windows or SQL Server editions.

- OS upgrades of physical servers without OEM hardware validation.

- Migration of applications that cannot tolerate an in-place OS or SQL engine upgrade.

- SQL clustering, Availability Groups, replication, SSRS, SSIS, SSAS, encryption, HSM, and third-party applications without an approved component-specific plan.

- Unsupported SQL features or third-party plugins.

- Application code remediation beyond agreed compatibility fixes.

4.0 Assumptions

| ID | Assumption | Required Action if False |
| --- | --- | --- |
| A-01 | Server is a VMware VM | Obtain physical-server/OEM upgrade validation and driver procedure |
| A-02 | A full, application-consistent backup exists | Stop change; complete and validate backup |
| A-03 | The VM can be restored or cloned | Use tested backup-restore rollback method |
| A-04 | Approved Windows Server 2022 media and keys are available | Obtain software entitlement and media hash validation |
| A-05 | Approved SQL Server 2022 media, product key, and licensing exist | Stop change until licensing is confirmed |
| A-06 | Local/domain privileged credentials are available | Test accounts before outage |
| A-07 | Application owner has approved downtime and validation tests | Reschedule or obtain approval |
| A-08 | SQL Server 2016 is fully patched to supported baseline | Patch or use approved remediation plan |
| A-09 | No pending OS restart exists before SQL upgrade | Restart and revalidate; Microsoft specifically cautions against installing/upgrading SQL Server 2022 on Windows Server 2022 with pending restarts. |
| A-10 | Upgrade has been rehearsed in a representative non-production environment | Escalate as exceptional high-risk change |

5.0 Risks and Controls

| Risk | Impact | Preventive Control | Recovery Control |
| --- | --- | --- | --- |
| OS upgrade failure | Server unavailable | Snapshot, backup, tested ISO, VMware Tools validation | Restore VM/snapshot or backup |
| SQL setup failure | Database service unavailable | SQL assessment, full system/DB backups, setup logs captured | Restore VM or SQL backup |
| Application incompatibility | Business outage | Application vendor certification and UAT | Roll back platform |
| Driver or VMware Tools issue | Network/storage loss | Upgrade VMware Tools and verify virtual hardware support | Console access and snapshot restore |
| Monitoring/backup agent failure | Reduced observability or recoverability | Vendor compatibility validation | Reinstall/reconfigure agent |
| Database performance regression | SLA breach | Baseline, Query Store, statistics strategy, staged compatibility-level change | Restore prior plan/configuration; rollback where needed |
| Encryption/key access failure | Databases unavailable | Back up certificates, keys, HSM configuration, service identities | Restore keys/configuration or full rollback |
| Incomplete backups | Irrecoverable data loss | Restore test and evidence review | Do not proceed |
| Credential/SPN issues | Application authentication failure | Export service accounts/SPNs; validate Kerberos | Re-register SPNs and restore service account settings |
| Extended outage | Business disruption | Stop/go checkpoints and defined backout deadline | Invoke rollback before point of no return |

Best Practice: For business-critical SQL workloads, use side-by-side migration or a rolling HA upgrade where feasible. In-place upgrade should be selected only after the risk, dependency, downtime, and rollback trade-offs are formally accepted.

6.0 Dependencies

| Dependency | Owner | Validation Evidence |
| --- | --- | --- |
| Approved change and outage | Change Manager | CAB record |
| Windows Server 2022 ISO | Windows Team | SHA-256 hash, source record |
| SQL Server 2022 ISO and CU | DBA Team | SHA-256 hash, media record |
| Product keys / KMS access | Software Asset Management | License confirmation |
| VMware snapshot capacity | VMware Team | Datastore free-space evidence |
| Backup success and restore test | Backup Team | Job ID and restore evidence |
| AV/EDR compatibility | Security Team | Vendor support matrix / approval |
| Monitoring agent support | Monitoring Team | Validation test results |
| Application validation scripts | Application Owner | Signed test plan |
| SQL feature assessment | DBA Team | Assessment report |
| DNS, firewall, load balancer | Network Team | Change/validation record |
| DR recovery readiness | DR Team | Recovery plan and contacts |

7.0 Target Audience

- Windows Infrastructure Engineers

- SQL Server DBAs

- VMware Administrators

- Application Support Teams

- Monitoring and Backup Teams

- Cybersecurity and IAM Teams

- Change Managers and CAB Members

- DR Operations Teams

- Internal Audit, Risk, and Compliance Teams

8.0 References

- Microsoft Learn: Windows Server upgrade planning and supported paths. Windows Server 2016 can upgrade directly to Windows Server 2022 on non-clustered systems, subject to stated restrictions.

- Microsoft Learn: SQL Server upgrade guidance. Direct SQL Server 2016 to SQL Server 2022 upgrade is supported.

- Microsoft Learn: SQL Server 2022 supported version and edition upgrades.[1]

- Microsoft Learn: SQL Server 2022 hardware and software requirements.[2]

- Microsoft Learn: SQL Server on Windows version requirements. SQL Server 2022 is supported on Windows Server 2016 and Windows Server 2022.[3]

- Organization Change Management Policy: [Policy ID]

- Organization Backup and Recovery Standard: [Policy ID]

- Organization Security Hardening Standard: [Policy ID]

- Organization DR and Business Continuity Standard: [Policy ID]

- MAS TRM / Cyber Hygiene controls, where applicable: [Internal compliance mapping reference]

9.0 Acronyms

| Acronym | Meaning |
| --- | --- |
| AG | Availability Group |
| AV | Antivirus |
| CAB | Change Advisory Board |
| CU | Cumulative Update |
| DBCC | Database Console Commands |
| DR | Disaster Recovery |
| EDR | Endpoint Detection and Response |
| FCI | Failover Cluster Instance |
| GPO | Group Policy Object |
| HSM | Hardware Security Module |
| IFI | Instant File Initialization |
| KMS | Key Management Service |
| OS | Operating System |
| RPO | Recovery Point Objective |
| RTO | Recovery Time Objective |
| SPN | Service Principal Name |
| SSAS | SQL Server Analysis Services |
| SSIS | SQL Server Integration Services |
| SSRS | SQL Server Reporting Services |
| TDE | Transparent Data Encryption |
| VM | Virtual Machine |

Part I — Windows Server 2016 to Windows Server 2022

10.0 Supported Upgrade Path

10.1 Approved Path

| Source OS | Target OS | In-Place Upgrade Status | Notes |
| --- | --- | --- | --- |
| Windows Server 2016 Standard | Windows Server 2022 Standard | Supported | Same language and installation type required |
| Windows Server 2016 Datacenter | Windows Server 2022 Datacenter | Supported | Same language and installation type required |
| Windows Server 2016 Standard | Windows Server 2022 Datacenter | Supported | Edition upgrade permitted with valid licensing |
| Windows Server 2016 Datacenter | Windows Server 2022 Standard | Not supported | Edition downgrade is not supported |
| Windows Server 2016 Core | Windows Server 2022 Core | Supported | Core-to-Core only |
| Windows Server 2016 Desktop Experience | Windows Server 2022 Desktop Experience | Supported | GUI-to-GUI only |
| Windows Server 2016 Failover Cluster node | Windows Server 2022 | Not via direct rolling upgrade | Cluster rolling upgrades advance one OS version at a time. |

Windows Server 2016 to Windows Server 2022 is within Microsoft’s supported two-release in-place upgrade limit for Windows Server 2022 and earlier.

10.2 Unsupported or Restricted Scenarios

| Scenario | Status | Required Alternative |
| --- | --- | --- |
| Server Core to Desktop Experience | Unsupported | Clean installation/migration |
| Desktop Experience to Server Core | Unsupported | Clean installation/migration |
| Different OS language | Unsupported | Migration or clean installation |
| Licensed OS to Evaluation target | Unsupported | Clean installation of Evaluation |
| Preview/pre-release OS | Unsupported | Clean installation |
| Boot from VHD | Unsupported | Migration or clean installation |
| Windows Storage Server | Unsupported | Migration |
| Datacenter to Standard | Unsupported | Rebuild/migration |
| NIC Teaming active | Restricted | Disable before upgrade and re-enable after |
| Domain controller retail conversion | Restricted | Follow DC-specific licensing/upgrade process |
| Failover Cluster rolling upgrade 2016 to 2022 | Unsupported directly | 2016 to 2019, then 2019 to 2022, or rebuild/migrate |

Microsoft states that Core/Desktop Experience switching, language changes, preview upgrades, evaluation-target upgrades, boot-from-VHD scenarios, and Windows Storage Server in-place upgrades are not supported. It also requires NIC Teaming to be disabled before the upgrade.

10.3 Licensing and Activation

| Item | Requirement |
| --- | --- |
| Licensing | Valid Windows Server 2022 entitlement for the target edition |
| Activation | KMS, MAK, Active Directory-based activation, or approved enterprise method |
| Edition retention | Standard normally upgrades to Standard; Datacenter normally upgrades to Datacenter |
| Edition upgrade | Standard to Datacenter is supported with valid entitlement |
| Evaluation media | Do not use to upgrade a licensed installation |
| Product key | Obtain from approved software asset-management process |
| Evidence | Capture slmgr /dlv, licensing approval, and activation result |

Warning: Do not proceed if the selected media edition, language, or installation type does not match the source configuration unless the change has an explicitly supported conversion path.

11.0 Hardware and VMware Requirements

11.1 Minimum and Recommended Baseline

| Component | Minimum / Requirement | Enterprise Recommendation | Validation |
| --- | --- | --- | --- |
| CPU | 64-bit, compatible processor | At least 2 vCPU; retain or improve existing sizing | VMware VM settings |
| RAM | At least 512 MB for Server Core; 2 GB for Desktop Experience | Maintain current allocation; evaluate workload baseline | systeminfo |
| OS disk | Adequate free space for setup, rollback artifacts, logs | Minimum 40 GB free on C:; more for SQL/application workloads | Get-Volume |
| Firmware | UEFI supported where configured | Preserve existing boot configuration | VM firmware setting |
| Secure Boot | Supported where configured | Enable only after compatibility validation | VMware VM options |
| TPM | Not mandatory for Windows Server 2022 installation | vTPM only where security design requires it | VMware VM hardware |
| Drivers | Supported guest drivers | Current VMware Tools and approved virtual drivers | VMware Tools version |
| VMware Tools | Supported version | Upgrade to approved current version before maintenance | vCenter inventory |
| VM compatibility | Supported by ESXi/vCenter version | Upgrade virtual hardware only in separate approved change | vCenter compatibility report |
| NIC | VMware virtual NIC supported by guest OS | VMXNET3 preferred, subject to application/vendor validation | Device Manager |
| Storage | Supported virtual SCSI controller | PVSCSI where approved for high-I/O SQL workloads | VM hardware settings |

Important: Do not combine a virtual hardware version upgrade, firmware mode change, virtual NIC change, or virtual SCSI controller change with the OS in-place upgrade unless specifically tested and approved. Limit change variables.

11.2 VMware Readiness Checklist

| Check | Command / Method | Expected Result |
| --- | --- | --- |
| vCenter/ESXi support | Review VMware Compatibility Guide and internal platform standard | Supported guest OS and hardware version |
| Snapshot capacity | Check datastore free space | Sufficient space for snapshot growth |
| VMware Tools | Get-ItemProperty 'HKLM:\SOFTWARE\VMware, Inc.\VMware Tools' | Approved supported version |
| Console access | Launch vCenter remote console | Console available without network dependency |
| VM backup | Confirm enterprise backup job | Latest successful backup and restore validation |
| Time sync | Validate VM and domain time configuration | No conflicting time source configuration |
| NIC type | vCenter VM settings | Approved NIC type and configuration |
| Disk controllers | vCenter VM settings | No unsupported or unapproved configuration |

12.0 Compatibility Assessment

12.1 Required Assessment Areas

| Area | Assessment Activity | Evidence |
| --- | --- | --- |
| Server roles | Identify all installed roles/features | Exported roles/features report |
| Applications | Inventory software and vendor support | Application compatibility sign-off |
| Drivers | Validate VMware virtual devices and any pass-through devices | Device Manager export |
| Security tooling | Confirm AV/EDR/DLP/PAM compatibility with Server 2022 | Security approval |
| Monitoring | Confirm SCOM, SolarWinds, Splunk/forwarder, Instana, Prometheus agent compatibility | Monitoring validation |
| Backup | Confirm backup agent and VSS support | Backup approval |
| Storage | Validate MPIO, iSCSI, Fibre Channel, filter drivers, encryption drivers | Storage assessment |
| VMware Tools | Confirm approved supported release | vCenter evidence |
| NIC Teaming | Determine whether active | Disable plan, if applicable |
| PowerShell/.NET | Identify scripts and runtime dependencies | Script/application assessment |
| Certificates | Export certificate inventory and private key dependencies | Certificate register |
| SQL workload | Assess database engine, SQL features, HA, encryption, drivers | DBA assessment report |

12.2 PowerShell Inventory Commands

# OS and hardware baseline
Get-ComputerInfo | Out-File C:\UpgradeEvidence\ComputerInfo_Pre.txt
systeminfo | Out-File C:\UpgradeEvidence\SystemInfo_Pre.txt

# Installed roles and features
Get-WindowsFeature | Where-Object Installed | Sort-Object Name |
    Export-Csv C:\UpgradeEvidence\WindowsFeatures_Pre.csv -NoTypeInformation

# Installed applications
Get-ItemProperty HKLM:\Software\Microsoft\Windows\CurrentVersion\Uninstall\*,
                 HKLM:\Software\Wow6432Node\Microsoft\Windows\CurrentVersion\Uninstall\* |
    Where-Object DisplayName |
    Select-Object DisplayName, DisplayVersion, Publisher, InstallDate |
    Sort-Object DisplayName |
    Export-Csv C:\UpgradeEvidence\InstalledApplications_Pre.csv -NoTypeInformation

# Drivers
Get-CimInstance Win32_PnPSignedDriver |
    Select-Object DeviceName, DriverVersion, DriverDate, Manufacturer |
    Export-Csv C:\UpgradeEvidence\Drivers_Pre.csv -NoTypeInformation

# Services and scheduled tasks
Get-Service | Sort-Object Name |
    Export-Csv C:\UpgradeEvidence\Services_Pre.csv -NoTypeInformation

Get-ScheduledTask | Select-Object TaskName, TaskPath, State |
    Export-Csv C:\UpgradeEvidence\ScheduledTasks_Pre.csv -NoTypeInformation

12.3 Compatibility Decision Matrix

| Condition | Decision | Required Action |
| --- | --- | --- |
| All critical applications supported | Proceed | Continue through CAB gates |
| Application support unknown | Conditional hold | Obtain vendor confirmation or complete UAT |
| Unsupported driver/filter driver | Do not proceed | Upgrade/remove component or choose migration |
| Unsupported backup/AV/monitoring agent | Do not proceed | Upgrade agent and validate first |
| Active NIC Teaming | Remediate | Disable before OS upgrade |
| Domain controller / CA / cluster node | Specialist procedure required | Use role-specific upgrade plan |
| SQL FCI / AG / replication | DBA topology plan required | Use planned sequence and failover approach |
| Snapshot/backup not validated | Do not proceed | Correct and revalidate |

13.0 Windows Pre-Upgrade Checklist

13.1 Evidence Requirements

Create an evidence folder with restricted access:

New-Item -Path C:\UpgradeEvidence -ItemType Directory -Force
$Date = Get-Date -Format yyyyMMdd_HHmm
Start-Transcript -Path "C:\UpgradeEvidence\Windows_PreUpgrade_$Date.log"

13.2 Detailed Checklist

| Check | Purpose | PowerShell / Command | Expected Result | Interpretation / Evidence |
| --- | --- | --- | --- | --- |
| Windows version | Confirm source version/edition/build | Get-ComputerInfo \¦ Select WindowsProductName, WindowsVersion, OsBuildNumber | Windows Server 2016 | Capture output |
| Hostname | Confirm target identity | $env:COMPUTERNAME | Matches approved change | Mismatch: stop and verify target |
| IP address | Preserve network settings | Get-NetIPAddress -AddressFamily IPv4 | Approved IPs listed | Capture all NICs |
| DNS servers | Validate name resolution config | Get-DnsClientServerAddress -AddressFamily IPv4 | Approved DNS IPs | Compare with CMDB |
| Gateway | Validate routing | Get-NetRoute -DestinationPrefix 0.0.0.0/0 | Approved default route | Validate metric/interface |
| Disk free space | Ensure setup capacity | Get-Volume | C: meets approved threshold | Expand disk if insufficient |
| Disk health | Detect storage failures | Get-PhysicalDisk \¦ Get-StorageReliabilityCounter | Healthy where supported | Escalate storage errors |
| BitLocker | Identify encryption state | manage-bde -status | Documented state and recovery keys secured | Suspend if required by design |
| Pending reboot | Avoid setup failure | See script below | No pending reboot | Reboot and revalidate if present |
| Windows updates | Ensure approved baseline | Get-HotFix | Latest approved patch baseline | Record KBs |
| Services | Capture runtime baseline | Get-Service | Critical services running | Record exceptions |
| Domain membership | Confirm AD relationship | Get-CimInstance Win32_ComputerSystem | Correct domain and role | Validate secure channel |
| FSMO role | Required only if DC | netdom query fsmo | Roles identified | DC-specific plan required |
| Time synchronization | Prevent Kerberos/TLS issues | w32tm /query /status | Correct source/offset | Correct material drift |
| Certificates | Preserve application trust | Get-ChildItem Cert:\LocalMachine\My | Inventory exported | Export private keys as approved |
| Scheduled tasks | Preserve operational automation | Get-ScheduledTask | Inventory captured | Validate tasks after upgrade |
| Firewall rules | Preserve connectivity | Get-NetFirewallRule | Rules exported | Compare post-upgrade |
| GPO | Capture applied policy | gpresult /h C:\UpgradeEvidence\GPResult_Pre.html | Report generated | Compare post-upgrade |
| Activation | Validate source license state | slmgr /xpr | Activated | Resolve before upgrade |
| Installed applications | Detect dependencies | Installed-app inventory script | Inventory complete | Vendor validation required |
| Event Viewer | Identify pre-existing errors | Get-WinEvent query | No unresolved critical errors | Baseline known issues |
| Performance baseline | Detect regression later | PerfMon / scripts | CPU, RAM, disk baseline | Store artefacts |
| Open ports | Capture service exposure | Get-NetTCPConnection -State Listen | Known ports only | Review anomalies |
| SMB configuration | Preserve security controls | Get-SmbServerConfiguration | Existing policy recorded | Compare post-upgrade |
| RDP access | Confirm alternate management path | Test-NetConnection localhost -Port 3389 | Listening if RDP required | Use console fallback |
| Admin access | Confirm recovery access | Test approved break-glass account | Successful login | Do not proceed without it |
| Recovery partition | Confirm recovery configuration | reagentc /info | Record state | Informative; not a rollback substitute |
| Backup status | Confirm recoverability | Backup console / job ID | Successful backup | Evidence mandatory |
| Snapshot strategy | Confirm rapid rollback | vCenter verification | Approved snapshot window/capacity | Avoid long-lived snapshot |

13.3 Pending-Reboot Check

$PendingReboot = @(
    Test-Path 'HKLM:\SOFTWARE\Microsoft\Windows\CurrentVersion\Component Based Servicing\RebootPending'
    Test-Path 'HKLM:\SOFTWARE\Microsoft\Windows\CurrentVersion\WindowsUpdate\Auto Update\RebootRequired'
    (Get-ItemProperty 'HKLM:\SYSTEM\CurrentControlSet\Control\Session Manager' `
        -Name PendingFileRenameOperations -ErrorAction SilentlyContinue) -ne $null
)

if ($PendingReboot -contains $true) {
    Write-Output 'PENDING REBOOT DETECTED'
} else {
    Write-Output 'NO PENDING REBOOT DETECTED'
}

13.4 Performance Baseline Commands

Get-Counter '\Processor(_Total)\% Processor Time',
            '\Memory\Available MBytes',
            '\LogicalDisk(*)\% Free Space',
            '\LogicalDisk(*)\Avg. Disk sec/Read',
            '\LogicalDisk(*)\Avg. Disk sec/Write' `
            -SampleInterval 15 -MaxSamples 20 |
Export-Counter -Path C:\UpgradeEvidence\PerfBaseline_Pre.blg -Force

Tip: Capture at least one representative business-period baseline for SQL workloads. A short idle-time sample alone is insufficient for meaningful post-upgrade comparison.

13.5 Representative Screenshot Placeholders

| Figure | Screenshot Required | Engineer Must Verify |
| --- | --- | --- |
| Figure 1 | Windows Server 2016 desktop / Server Manager | Server name, source OS, role state, no unexpected alerts |
| Figure 2 | winver on source server | Windows Server 2016 edition and build |
| Figure 3 | Disk Management / File Explorer | OS disk free space and data disk layout |
| Figure 4 | Backup console | Successful backup job, timestamp, retention |
| Figure 5 | vCenter VM summary | VM name, power state, snapshot status, datastore capacity |
| Figure 6 | Monitoring dashboard | Healthy availability and baseline metrics before outage |

14.0 Windows Backup and Rollback Strategy

14.1 Required Recovery Layers

| Recovery Layer | Requirement | Owner | Validation |
| --- | --- | --- | --- |
| VMware snapshot | Create immediately before upgrade, only after backup validation | VMware Team | Snapshot creation timestamp |
| VM backup | Successful full/application-consistent backup | Backup Team | Job result and restore evidence |
| System state backup | Required for AD DS/DC and other relevant roles | Windows Team | Backup report |
| File backup | Required for non-database application data | Application/Backup Team | Backup report |
| SQL backup | Full backup of all databases and system databases | DBA Team | Restore verification |
| Configuration export | Roles, services, firewall, tasks, certificates, registry, SQL configs | Windows/DBA | Evidence folder |
| Restore test | Restore test within agreed RPO/RTO | Backup/DR Team | Test result |

14.2 Snapshot Rules

- Create the snapshot only after backups complete successfully.

- Quiesce the guest only if supported and validated by the backup/VMware design.

- Record snapshot name: [ServerName]_PreWin2022Upgrade_[YYYYMMDD_HHMM].

- Do not retain snapshots longer than the approved rollback window.

- Do not rely on a VMware snapshot as the sole backup or long-term rollback mechanism.

- Confirm datastore capacity and snapshot growth risk, especially for write-intensive SQL Servers.

Warning: Snapshot restoration may revert OS, SQL binaries, data disks, and configuration to the capture point. For systems processing transactions, explicitly assess data-loss exposure between snapshot creation and rollback.

15.0 Windows Server In-Place Upgrade Procedure

15.1 Implementation Roles

| Activity | Primary | Backup |
| --- | --- | --- |
| Change coordination | Change Manager | Infrastructure Manager |
| OS upgrade | Windows Engineer | Windows Engineer 2 |
| VMware operations | VMware Engineer | VMware Engineer 2 |
| SQL controls | DBA | DBA 2 |
| Backup validation | Backup Engineer | Backup Engineer 2 |
| Application validation | Application Owner | Application Support |
| Security validation | Security Operations | Platform Security |
| Monitoring validation | Monitoring Engineer | Operations Team |

15.2 Stop/Go Gates

| Gate | Condition | Decision Authority |
| --- | --- | --- |
| Gate 1 | CAB approval and outage confirmation | Change Manager |
| Gate 2 | Backup, restore evidence, and snapshot capacity confirmed | Backup/VMware Owners |
| Gate 3 | Application shutdown confirmation | Application Owner |
| Gate 4 | Pre-check evidence has no blocking findings | Windows/DBA Leads |
| Gate 5 | Windows setup compatibility assessment passed | Windows Lead |
| Gate 6 | OS validation passed | Windows Lead + Application Owner |
| Gate 7 | SQL/app validation passed | DBA + Application Owner |
| Gate 8 | Backout deadline reached without success | Change Manager / Technical Lead |

15.3 Procedure Steps

| Step | Activity | Purpose | Command / GUI Navigation | Expected Output | Est. Duration | Risk / Decision / Rollback Point |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Start change bridge | Establish controlled communications | Open approved bridge/channel; record participants | All owners present | 10 min | Stop if mandatory owners unavailable |
| 2 | Confirm outage notification | Ensure stakeholder awareness | Use approved communication template | Notification sent | 5 min | Stop if business approval absent |
| 3 | Validate server identity | Prevent wrong-server change | hostname; compare CMDB, vCenter, change record | Identity confirmed | 5 min | Stop on mismatch |
| 4 | Capture final baseline | Preserve before-state evidence | Run Section 13 scripts | Artefacts saved | 15 min | Evidence mandatory |
| 5 | Confirm backup success | Establish recoverability | Review backup console/job IDs | Successful and within RPO | 10 min | Rollback prerequisite |
| 6 | Stop application workload | Achieve a consistent state | Application-specific stop procedure | Application services stopped | 15–60 min | App owner approval mandatory |
| 7 | Stop SQL services if approved | Prevent active transaction activity | Stop-Service MSSQLSERVER or named service procedure | SQL services stopped | 5–20 min | DBA approval required |
| 8 | Disable NIC Teaming, if present | Meet OS upgrade restriction | Use approved networking procedure | Team disabled; individual NIC validated | 10–30 min | Microsoft requires disabling NIC Teaming before upgrade. |
| 9 | Disable non-essential agents only if approved | Prevent filter-driver/setup conflict | Stop approved AV/backup/monitoring services | Services stopped | 5–15 min | Do not disable EDR without security approval |
| 10 | Create VMware snapshot | Provide rapid rollback option | vCenter > VM > Snapshots > Take Snapshot | Snapshot completed | 5–30 min | Rollback Point A |
| 11 | Mount Server 2022 ISO | Start setup from running OS | vCenter > Edit Settings > CD/DVD > Datastore ISO; connect ISO | ISO visible in guest | 5 min | Validate correct, trusted media |
| 12 | Launch setup | Begin in-place workflow | Run setup.exe from mounted ISO as Administrator | Windows Setup opens | 5 min | Capture Figure 7 |
| 13 | Download updates selection | Select approved setup update option | Windows Setup > Change how Setup downloads updates | Choice per policy | 5–30 min | If offline, document compensating control |
| 14 | Enter product key | Select licensed target | Setup > Product Key | Valid key accepted | 2 min | Stop if edition mismatch |
| 15 | Select edition | Preserve correct edition/install type | Choose matching Standard/Datacenter and Core/Desktop Experience | Matching option selected | 2 min | Capture Figure 8 |
| 16 | Accept license terms | Proceed with legal terms | Setup > Accept | Continue enabled | 2 min | Capture Figure 9 |
| 17 | Select upgrade option | Preserve apps/data/configuration | Choose Keep files, settings, and apps | Upgrade path selected | 2 min | Stop if only clean install is offered |
| 18 | Review compatibility report | Identify blockers | Setup compatibility assessment | No blocking issues | 10–30 min | Gate 5; capture Figure 10 |
| 19 | Record warnings | Retain audit evidence | Screenshot/save report | Warnings approved | 5 min | Stop if unresolved blocker |
| 20 | Start installation | Begin OS replacement | Select Install | Upgrade begins | 5 min | Rollback Point B ends once irreversible changes advance |
| 21 | Monitor progress | Track upgrade health | Console/vCenter; do not interrupt | Progress through copying/installing/configuring | 45–180 min | Multiple reboots expected |
| 22 | Verify reboot/login | Confirm operating system startup | vCenter console, approved admin account | Server starts and login succeeds | 15 min | If failure: evaluate rollback |
| 23 | Confirm OS version | Verify target state | winver; Get-ComputerInfo | Windows Server 2022 | 5 min | Capture Figure 11 |
| 24 | Verify services/network | Confirm critical platform functions | Run post-upgrade commands | No critical failures | 15–30 min | Gate 6 |
| 25 | Re-enable NIC Teaming | Restore approved network design | Approved NIC teaming procedure | Team active / connectivity confirmed | 10–30 min | Validate routes/DNS |
| 26 | Re-enable agents | Restore protection/observability | Start/reinstall validated agents | Agents healthy | 15–45 min | Do not close change without this |
| 27 | Apply approved updates | Bring OS to approved patch level | Windows Update / WSUS / MECM | Updates installed; reboot complete | 30–120 min | May require extra outage |
| 28 | Complete application/SQL validation | Confirm service restoration | Execute validation scripts | Business tests passed | 30–120 min | Gate 7 |
| 29 | Remove snapshot | End temporary rollback state | vCenter > Delete snapshot after approval | Snapshot consolidated | 10–60 min | Only after formal success confirmation |
| 30 | Close change | Document outcome | Attach evidence, timings, exceptions | CAB/change records updated | 15 min | Record lessons learned |

15.4 Setup Screen Figure Register

| Figure | Representative Screen | What to Verify |
| --- | --- | --- |
| Figure 7 | Windows Server 2022 Setup – initial screen | Correct ISO/media, setup launched from existing Server 2016 OS |
| Figure 8 | Product key / edition selection | Correct Windows Server 2022 edition, matching installation type |
| Figure 9 | License terms | Correct target product; terms accepted |
| Figure 10 | Ready to install / compatibility screen | “Keep files, settings, and apps” selected; no blocking issues |
| Figure 11 | Upgrade progress | Progress is advancing; do not power off or disconnect ISO |
| Figure 12 | Reboot/login screen | Server rebooted normally; approved administrator login available |
| Figure 13 | Windows Server 2022 desktop | Correct server identity, no persistent setup errors |
| Figure 14 | Server Manager | Expected roles displayed, no critical management alerts |
| Figure 15 | winver | Windows Server 2022 edition/build |
| Figure 16 | System Information | Correct OS name, system type, installed memory, domain membership |

16.0 Windows Post-Upgrade Tasks

| Activity | Command / Method | Expected Result | Evidence |
| --- | --- | --- | --- |
| Validate OS version | Get-ComputerInfo | Windows Server 2022 target build | Screenshot/output |
| Validate activation | slmgr /xpr | Activated | Screenshot/output |
| Apply approved OS updates | WSUS/MECM/Windows Update | Current approved baseline | Patch report |
| Confirm VMware Tools | VMware Tools UI/vCenter | Running approved version | vCenter screenshot |
| Validate drivers | Device Manager / Get-PnpDevice | No unknown/error devices | Export |
| Confirm AV/EDR | Vendor console and service check | Protected and reporting | Console evidence |
| Confirm monitoring | SCOM/SolarWinds/Splunk/etc. | Host healthy, telemetry received | Dashboard evidence |
| Confirm backup agent | Backup console/job test | Successful backup | Job ID |
| Validate DNS | Resolve-DnsName [FQDN] | Expected responses | Output |
| Validate network | Test-NetConnection [Dependency] -Port [Port] | TCP success | Output |
| Validate domain trust | Test-ComputerSecureChannel -Verbose | True | Output |
| Refresh GPO | gpupdate /force; gpresult /h | Policies applied | HTML report |
| Review event logs | See commands below | No unapproved critical errors | Event export |
| Validate services | Get-Service | Required services running | Comparison report |
| Validate tasks | Get-ScheduledTask | Required tasks enabled/successful | Screenshot/export |
| Validate firewall | Get-NetFirewallRule | Expected rules present/enabled | Export |
| Validate certificates | Get-ChildItem Cert:\LocalMachine\My | Expected certs available/not expired | Inventory |
| Validate RDP/console | Remote login and vCenter console | Both methods available as designed | Test evidence |
| Validate performance | PerfMon vs baseline | No material unexplained degradation | Baseline comparison |
| Validate disk health | Get-Volume; storage logs | Volumes healthy, expected capacity | Output |
| Confirm time source | w32tm /query /status | Approved source/offset | Output |

16.1 Event Log Review

$StartTime = (Get-Date).AddHours(-4)

Get-WinEvent -FilterHashtable @{
    LogName = 'System'
    Level = 1,2
    StartTime = $StartTime
} | Select-Object TimeCreated, Id, ProviderName, LevelDisplayName, Message |
Export-Csv C:\UpgradeEvidence\SystemCriticalErrors_Post.csv -NoTypeInformation

Get-WinEvent -FilterHashtable @{
    LogName = 'Application'
    Level = 1,2
    StartTime = $StartTime
} | Select-Object TimeCreated, Id, ProviderName, LevelDisplayName, Message |
Export-Csv C:\UpgradeEvidence\ApplicationCriticalErrors_Post.csv -NoTypeInformation

17.0 Windows Validation Record

| ID | Validation Item | Command / Test | Expected Result | Pass / Fail | Evidence Reference | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| W-01 | OS version | winver | Windows Server 2022 | [ ] | [Path] | Windows |
| W-02 | Activation | slmgr /xpr | Activated | [ ] | [Path] | Windows |
| W-03 | Domain trust | Test-ComputerSecureChannel | True | [ ] | [Path] | Windows |
| W-04 | DNS | Resolve-DnsName | Correct records | [ ] | [Path] | Windows |
| W-05 | Network | Test-NetConnection | Required ports reachable | [ ] | [Path] | Network |
| W-06 | Critical services | Get-Service | Running | [ ] | [Path] | Windows |
| W-07 | Monitoring | Monitoring console | Host healthy | [ ] | [Path] | Monitoring |
| W-08 | Backup | Backup job / test | Successful | [ ] | [Path] | Backup |
| W-09 | AV/EDR | Security console | Active/reporting | [ ] | [Path] | Security |
| W-10 | Event logs | Event log query | No critical unresolved errors | [ ] | [Path] | Windows |
| W-11 | Application | Business test script | Passed | [ ] | [Path] | Application |
| W-12 | Performance | Baseline comparison | Within approved tolerance | [ ] | [Path] | Windows/DBA |

Part II — SQL Server 2016 to SQL Server 2022

18.0 SQL Upgrade Strategy and Sequence

18.1 Recommended Sequence

For a SQL Server 2016 instance hosted on Windows Server 2016:

- Complete SQL Server 2016 assessment and backups.

- Upgrade SQL Server 2016 to SQL Server 2022 while still running on Windows Server 2016, where the environment’s approved design supports this sequence.

- Validate SQL Server 2022, applications, monitoring, backup, HA, and security controls.

- Upgrade Windows Server 2016 to Windows Server 2022.

- Apply approved SQL Server 2022 cumulative update, validate SQL functionality, and complete business testing.

SQL Server 2022 is supported on both Windows Server 2016 and Windows Server 2022, allowing this staged approach. Microsoft also supports direct upgrades from SQL Server 2016 to SQL Server 2022.[3]

Warning: Do not automatically raise database compatibility level immediately after an engine upgrade. Keep the existing compatibility level initially, validate workload behavior, then raise it using a separate, approved performance-validation step.

18.2 SQL Upgrade Eligibility

| Condition | Requirement |
| --- | --- |
| Source version | SQL Server 2016 (13.x) |
| Target version | SQL Server 2022 (16.x) |
| Edition | Confirm supported source-to-target edition upgrade path |
| OS | Confirm installed SQL 2022 build supports source and target OS |
| SQL patch level | Bring source to approved latest SQL Server 2016 servicing baseline before upgrade |
| Feature support | Assess every installed SQL feature individually |
| Setup account | Local administrator; SQL sysadmin; access to media/log locations |
| Free disk | Adequate setup, temp, log, and rollback capacity |
| Reboot status | No pending OS reboot before SQL setup on Windows Server 2022. |
| Backup | Full database/system/database-object/configuration backup and restore validation |
| HA/DR | Specific topology execution and rollback plan approved |
| Application | Vendor support and business validation script approved |

19.0 SQL Compatibility Assessment

19.1 Instance and Feature Discovery

SELECT
    SERVERPROPERTY('ServerName') AS ServerName,
    SERVERPROPERTY('InstanceName') AS InstanceName,
    SERVERPROPERTY('Edition') AS Edition,
    SERVERPROPERTY('ProductVersion') AS ProductVersion,
    SERVERPROPERTY('ProductLevel') AS ProductLevel,
    SERVERPROPERTY('ProductUpdateLevel') AS ProductUpdateLevel,
    SERVERPROPERTY('ProductUpdateReference') AS ProductUpdateReference,
    SERVERPROPERTY('IsClustered') AS IsClustered,
    SERVERPROPERTY('IsHadrEnabled') AS IsHadrEnabled;
GO

SELECT @@VERSION AS SqlVersion;
GO

SELECT
    servicename,
    startup_type_desc,
    status_desc,
    last_startup_time,
    service_account,
    filename
FROM sys.dm_server_services;
GO

19.2 Assessment Checklist

| Area | Purpose | Query / Method | Expected Result | Interpretation |
| --- | --- | --- | --- | --- |
| Edition | Confirm licensing/feature alignment | SERVERPROPERTY('Edition') | Approved target edition | Standard/Enterprise features assessed |
| Instances | Identify default/named instances | SQL Configuration Manager; registry; services | Full instance register | Each instance has a plan |
| Installed features | Determine upgrade impacts | SQL Setup discovery report | Feature inventory | Validate DB Engine, SSIS, SSAS, SSRS, etc. |
| Replication | Identify topology dependencies | sp_helpreplicationdboption / Replication Monitor | Status documented | Use replication-specific sequence |
| SSIS | Identify packages/catalogs | SSISDB query / SSISDB backup | Inventory complete | Validate catalog upgrade |
| SSRS | Identify SSRS deployment | Report Server DB/configuration | Inventory/backup complete | SSRS may require separate migration approach |
| SSAS | Identify tabular/multidimensional services | SSAS configuration | Inventory complete | Component-specific upgrade plan |
| Always On | Identify AG configuration | sys.availability_groups | Nodes/replicas documented | Rolling upgrade plan required |
| Log shipping | Identify shipping pairs | msdb.dbo.log_shipping_* | Configuration documented | Coordinate primary/secondary |
| Mirroring | Identify legacy mirroring | sys.database_mirroring | Status documented | Plan modernization/validated compatibility |
| Linked servers | Preserve connectivity | sys.servers | Inventory complete | Test drivers/security post-upgrade |
| CLR | Identify assemblies | sys.assemblies | Assemblies documented | Validate CLR/security setting |
| Service Broker | Identify queues/routes | Broker system views | Inventory complete | Validate endpoints/routes |
| Database Mail | Preserve notifications | msdb views | Profiles/accounts captured | Test SMTP post-upgrade |
| Maintenance Plans | Preserve scheduled maintenance | SSMS/MSDB inventory | Plans captured | Test jobs and schedules |
| SQL Agent jobs | Preserve automation | msdb.dbo.sysjobs | Jobs scripted/exported | Validate owners/proxies |
| Credentials | Preserve agent/integration access | sys.credentials | Inventory encrypted/secured | Recreate if needed |
| Certificates | Preserve encryption/TDE use | sys.certificates | Backed up with keys | Mandatory for encrypted DB restore |
| TDE | Ensure recovery keys | sys.dm_database_encryption_keys | Cert/key backup confirmed | Test restore mandatory |
| Database size | Estimate time/capacity | sys.master_files | Baseline captured | Size drives backup/restore planning |
| I/O performance | Detect pre-existing issue | PerfMon/DMVs | Baseline captured | Compare post-upgrade |
| CPU/memory | Baseline engine behavior | DMVs/PerfMon | Baseline captured | Compare post-upgrade |
| Blocking/deadlocks | Identify application issues | DMVs/XE/error log | Baseline known | Avoid attributing old issues to upgrade |
| Wait stats | Identify bottlenecks | sys.dm_os_wait_stats | Baseline captured | Reset only under controlled plan |
| MAXDOP/cost threshold | Capture tuning config | sys.configurations | Settings documented | Review based on CPU topology |
| TempDB | Capture files/configuration | tempdb.sys.database_files | Files/sizes/growth documented | Verify after upgrade |
| Collation | Preserve data behavior | SERVERPROPERTY('Collation') | Captured | Do not change during upgrade |
| Compatibility level | Stage behavior change | sys.databases | Existing values documented | Raise separately after validation |

20.0 SQL Pre-Upgrade Checks

20.1 Server and Database Baseline

-- SQL version and instance metadata
SELECT @@VERSION AS SqlVersion;
SELECT
    SERVERPROPERTY('MachineName') AS MachineName,
    SERVERPROPERTY('ServerName') AS ServerName,
    SERVERPROPERTY('InstanceName') AS InstanceName,
    SERVERPROPERTY('Edition') AS Edition,
    SERVERPROPERTY('ProductVersion') AS ProductVersion,
    SERVERPROPERTY('Collation') AS ServerCollation,
    SERVERPROPERTY('IsClustered') AS IsClustered,
    SERVERPROPERTY('IsHadrEnabled') AS IsHadrEnabled;
GO

-- Database state, compatibility, and recovery models
SELECT
    name,
    state_desc,
    user_access_desc,
    recovery_model_desc,
    compatibility_level,
    page_verify_option_desc,
    log_reuse_wait_desc,
    is_read_only,
    is_encrypted
FROM sys.databases
ORDER BY name;
GO

-- Database size
SELECT
    DB_NAME(database_id) AS DatabaseName,
    CAST(SUM(size) * 8.0 / 1024 AS decimal(18,2)) AS SizeMB
FROM sys.master_files
GROUP BY database_id
ORDER BY SizeMB DESC;
GO

20.2 Integrity Validation

-- Execute separately for each user database during the approved pre-check window
DBCC CHECKDB (N'[DatabaseName]') WITH NO_INFOMSGS, ALL_ERRORMSGS;
GO

Warning: A successful DBCC CHECKDB must be recorded before proceeding. Resolve consistency errors or obtain explicit risk acceptance and a recovery plan before upgrade.

20.3 SQL Agent, Jobs, and Maintenance

-- SQL Server Agent status
SELECT servicename, status_desc, startup_type_desc, service_account
FROM sys.dm_server_services
WHERE servicename LIKE 'SQL Server Agent%';
GO

-- Jobs
SELECT
    j.name AS JobName,
    j.enabled,
    SUSER_SNAME(j.owner_sid) AS JobOwner,
    c.name AS CategoryName,
    j.date_created,
    j.date_modified
FROM msdb.dbo.sysjobs AS j
LEFT JOIN msdb.dbo.syscategories AS c
    ON j.category_id = c.category_id
ORDER BY j.name;
GO

-- Job schedules
SELECT
    j.name AS JobName,
    s.name AS ScheduleName,
    s.enabled,
    s.freq_type,
    s.active_start_date,
    s.active_start_time
FROM msdb.dbo.sysjobs AS j
JOIN msdb.dbo.sysjobschedules AS js
    ON j.job_id = js.job_id
JOIN msdb.dbo.sysschedules AS s
    ON js.schedule_id = s.schedule_id
ORDER BY j.name, s.name;
GO

-- Database Mail
SELECT profile_id, name, description
FROM msdb.dbo.sysmail_profile;
GO

SELECT name, email_address, display_name, servername, port, enable_ssl
FROM msdb.dbo.sysmail_account;
GO

20.4 Linked Servers, Endpoints, and Security

-- Linked servers
SELECT
    name,
    product,
    provider,
    data_source,
    is_linked,
    is_remote_login_enabled,
    is_rpc_out_enabled,
    is_data_access_enabled
FROM sys.servers
WHERE server_id <> 0;
GO

-- Endpoints
SELECT
    name,
    type_desc,
    state_desc,
    protocol_desc,
    port
FROM sys.endpoints;
GO

-- Certificates
SELECT
    name,
    subject,
    issuer_name,
    expiry_date,
    pvt_key_encryption_type_desc
FROM sys.certificates;
GO

-- Logins
SELECT
    name,
    type_desc,
    is_disabled,
    default_database_name,
    create_date,
    modify_date
FROM sys.server_principals
WHERE type IN ('S','U','G')
ORDER BY type_desc, name;
GO

-- Credentials
SELECT name, credential_identity, create_date, modify_date
FROM sys.credentials;
GO

20.5 TDE and Encryption

SELECT
    DB_NAME(dek.database_id) AS DatabaseName,
    dek.encryption_state,
    dek.encryption_state_desc,
    dek.key_algorithm,
    dek.key_length,
    c.name AS CertificateName,
    c.expiry_date AS CertificateExpiryDate
FROM sys.dm_database_encryption_keys AS dek
LEFT JOIN master.sys.certificates AS c
    ON dek.encryptor_thumbprint = c.thumbprint;
GO

20.6 Configuration, TempDB, IFI, and Ports

-- Server configuration
SELECT
    name,
    value,
    value_in_use,
    minimum,
    maximum,
    description
FROM sys.configurations
ORDER BY name;
GO

-- TempDB file configuration
USE tempdb;
GO
SELECT
    name,
    physical_name,
    size * 8.0 / 1024 AS SizeMB,
    max_size,
    growth,
    is_percent_growth
FROM sys.database_files;
GO

-- SQL port information from error log
EXEC xp_readerrorlog 0, 1, N'Server is listening on';
GO

-- IFI indicator from error log, where logged
EXEC xp_readerrorlog 0, 1, N'Instant File Initialization';
GO

20.7 SPNs and Service Accounts

# Run using an account with Active Directory read permissions.
setspn -L "[DOMAIN\SqlServiceAccount]"
setspn -Q MSSQLSvc/[ServerFQDN]:[Port]
setspn -Q MSSQLSvc/[ServerShortName]:[Port]

20.8 Baseline Performance Queries

-- Top waits: capture before upgrade; exclude idle waits according to internal DBA standard
SELECT TOP (30)
    wait_type,
    waiting_tasks_count,
    wait_time_ms,
    max_wait_time_ms,
    signal_wait_time_ms
FROM sys.dm_os_wait_stats
ORDER BY wait_time_ms DESC;
GO

-- Active requests and blocking
SELECT
    r.session_id,
    r.status,
    r.command,
    r.cpu_time,
    r.total_elapsed_time,
    r.logical_reads,
    r.reads,
    r.writes,
    r.wait_type,
    r.wait_time,
    r.blocking_session_id,
    DB_NAME(r.database_id) AS DatabaseName,
    s.host_name,
    s.program_name,
    s.login_name
FROM sys.dm_exec_requests AS r
JOIN sys.dm_exec_sessions AS s
    ON r.session_id = s.session_id
WHERE r.session_id <> @@SPID;
GO

-- Deadlock-related system health event availability
SELECT name, startup_state
FROM sys.server_event_sessions
WHERE name = 'system_health';
GO

20.9 SQL Pre-Upgrade Checklist

| Check | Purpose | Expected Result | Pass / Fail | Evidence |
| --- | --- | --- | --- | --- |
| SQL version | Confirm upgrade source | SQL Server 2016 build recorded | [ ] | [Path] |
| SQL edition | Validate target entitlement | Approved edition | [ ] | [Path] |
| Instance inventory | Avoid missed named instances | All instances listed | [ ] | [Path] |
| Features inventory | Assess feature support | All installed features identified | [ ] | [Path] |
| DBCC CHECKDB | Validate consistency | No errors | [ ] | [Path] |
| Database status | Ensure online/healthy | All required DBs online | [ ] | [Path] |
| Backups | Ensure recoverability | Full/log/system DB backups successful | [ ] | [Path] |
| TDE certificates | Enable encrypted restore | Exported and tested | [ ] | [Path] |
| SQL Agent jobs | Preserve automation | Jobs scripted/exported | [ ] | [Path] |
| Linked servers | Preserve integration | Connectivity tested/documented | [ ] | [Path] |
| Service accounts | Preserve service startup/auth | Accounts and rights documented | [ ] | [Path] |
| SPNs | Preserve Kerberos | Expected SPNs documented | [ ] | [Path] |
| Network ports | Preserve application connectivity | Ports documented/testable | [ ] | [Path] |
| HA/DR | Protect availability | Topology plan approved | [ ] | [Path] |
| Monitoring | Preserve observability | Alerts/dashboards baselined | [ ] | [Path] |
| Performance | Detect regression | CPU, memory, I/O, waits captured | [ ] | [Path] |
| App validation | Confirm success criteria | Approved scripts available | [ ] | [Path] |

20.10 Required Screenshot Register

| Figure | Screenshot | Verify |
| --- | --- | --- |
| Figure 17 | SSMS connection / Object Explorer before upgrade | Correct instance and databases |
| Figure 18 | SQL Server Properties – General | Edition, version, product level, collation |
| Figure 19 | SQL Server Agent Jobs | Jobs enabled and expected schedules |
| Figure 20 | Database Properties – Options | Existing compatibility level and recovery model |
| Figure 21 | Always On dashboard, if applicable | Replica health and synchronization state |
| Figure 22 | SQL error log | No unresolved critical issue before upgrade |
| Figure 23 | Backup console | Successful full/system/transaction-log backups |

21.0 SQL Backup Strategy

21.1 Mandatory Backup Set

| Backup Item | Requirement | Example / Method | Validation |
| --- | --- | --- | --- |
| User databases | Full backup for every user DB | BACKUP DATABASE | RESTORE VERIFYONLY plus restore test |
| Differential backups | Perform where RPO/RTO requires | BACKUP DATABASE ... WITH DIFFERENTIAL | Job result |
| Transaction logs | Final tail-log backup where applicable | BACKUP LOG | Restore-chain validation |
| master | Full backup | BACKUP DATABASE master | Restore test |
| model | Full backup | BACKUP DATABASE model | Restore test |
| msdb | Full backup | BACKUP DATABASE msdb | Restore test |
| SSISDB | Full backup | BACKUP DATABASE SSISDB | Restore test |
| TDE certificate/key | Export certificate and private key | BACKUP CERTIFICATE | Secure storage verification |
| Service Master Key | Back up securely | BACKUP SERVICE MASTER KEY | Protected copy |
| Database Master Keys | Back up if used | BACKUP MASTER KEY | Protected copy |
| SQL Agent jobs | Script/export jobs and schedules | SSMS/PowerShell/SMO | Version-controlled export |
| Linked servers | Script configuration | SSMS/PowerShell | Reviewed script |
| Logins and SIDs | Script with SID/password hashes | Approved scripting method | Restore validation |
| Server configuration | Export sp_configure, registry, error logs | Scripts | Evidence folder |
| SSRS/SSAS/SSIS configs | Component-specific export | Vendor/Microsoft procedure | Restore validation |

21.2 Example Backup Commands

-- User database full backup
BACKUP DATABASE [DatabaseName]
TO DISK = N'[BackupPath]\DatabaseName_PreSQL2022Upgrade_FULL.bak'
WITH COMPRESSION, CHECKSUM, STATS = 10;
GO

RESTORE VERIFYONLY
FROM DISK = N'[BackupPath]\DatabaseName_PreSQL2022Upgrade_FULL.bak'
WITH CHECKSUM;
GO

-- System databases
BACKUP DATABASE [master]
TO DISK = N'[BackupPath]\master_PreSQL2022Upgrade_FULL.bak'
WITH COMPRESSION, CHECKSUM, STATS = 10;
GO

BACKUP DATABASE [msdb]
TO DISK = N'[BackupPath]\msdb_PreSQL2022Upgrade_FULL.bak'
WITH COMPRESSION, CHECKSUM, STATS = 10;
GO

21.3 TDE Certificate Backup

USE master;
GO

BACKUP CERTIFICATE [TDE_Certificate_Name]
TO FILE = N'[SecureBackupPath]\TDE_Certificate_Name.cer'
WITH PRIVATE KEY
(
    FILE = N'[SecureBackupPath]\TDE_Certificate_Name_PrivateKey.pvk',
    ENCRYPTION BY PASSWORD = N'[UseApprovedVaultManagedPassword]'
);
GO

Warning: Store TDE certificates, private keys, passwords, Service Master Key backups, and Database Master Key backups in an approved secrets-management or encrypted escrow location. Loss of the relevant certificate/private key can make an encrypted database backup unrecoverable.

21.4 Restore-Test Requirement

A representative restore test must demonstrate:

- Database backup readability.

- Certificate/key availability for encrypted databases.

- Recovery of a database to a non-production isolated environment.

- Login/SID and application connectivity validation where feasible.

- RTO and RPO alignment with the approved change plan.

22.0 SQL Server 2022 In-Place Upgrade Procedure

22.1 Pre-Implementation Conditions

| Condition | Required State |
| --- | --- |
| Approved SQL Server 2022 media | Available, hash-validated, stored securely |
| SQL Server 2022 CU | Approved current CU package available |
| OS status | No pending restart |
| SQL backups | Completed and validated |
| TDE / encryption keys | Backed up and verified |
| Business transaction control | Application stopped or read-only mode confirmed |
| SQL Agent | Non-essential jobs disabled or schedules suspended |
| Monitoring | Maintenance mode enabled with approved exception |
| HA/DR topology | Topology-specific plan approved |
| Rollback | Snapshot/backup recovery route approved |
| SQL Server setup logs path | Identified and writable |
| Downtime bridge | Active and staffed |

22.2 Standard Standalone Instance Procedure

| Step | Activity | Purpose | GUI / Command | Expected Result | Est. Duration | Risk / Rollback |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Start DBA implementation bridge | Coordinate execution | Approved bridge | Stakeholders present | 10 min | Stop if required owners absent |
| 2 | Confirm final transaction state | Ensure consistent application state | App owner/DBA validation | No active business processing | 10–30 min | Stop if transactions remain |
| 3 | Disable SQL Agent jobs | Prevent jobs running during outage | SQL Agent / job scripts | Non-essential jobs disabled | 5–15 min | Record original state |
| 4 | Capture final SQL evidence | Preserve current configuration | Run pre-check queries | Outputs stored | 15–30 min | Mandatory |
| 5 | Confirm full backup set | Establish database recoverability | Backup console and SQL history | Success confirmed | 10 min | Rollback prerequisite |
| 6 | Create VM snapshot | Provide rapid infrastructure rollback | vCenter snapshot procedure | Snapshot complete | 5–30 min | Rollback Point A |
| 7 | Mount SQL Server 2022 media | Start approved setup | Mount ISO; run as admin | Installation Center opens | 5 min | Validate media/version |
| 8 | Open Installation Center | Access upgrade workflow | Installation > Upgrade from a previous version | Setup begins | 5 min | Capture Figure 24 |
| 9 | Run Setup Support Rules | Identify prerequisites | Setup Support Rules | All required rules pass | 5–15 min | Capture Figure 25; stop on failure |
| 10 | Enter product key | Select licensed edition | Product Key page | Key accepted | 2 min | Stop on licensing issue |
| 11 | Accept license terms | Continue | License Terms page | Accepted | 2 min | Capture evidence |
| 12 | Microsoft Update choice | Apply policy-approved update method | Microsoft Update page | Decision recorded | 2 min | Use approved patch approach |
| 13 | Select instance | Identify exact SQL 2016 instance | Instance Selection | Correct instance selected | 2 min | Capture Figure 26 |
| 14 | Review Feature Rules | Confirm feature compatibility | Feature Rules page | No blocker | 5–15 min | Stop on failure |
| 15 | Review instance configuration | Preserve service/configuration | Instance Configuration page | Expected instance/service settings | 5 min | Validate service account |
| 16 | Review server configuration | Confirm service accounts/startup types | Server Configuration page | Matches pre-upgrade baseline | 5 min | Do not casually change accounts |
| 17 | Review full-text/other features | Confirm installed feature state | Relevant feature pages | Approved configuration | 5 min | Feature-specific validation |
| 18 | Review upgrade rules | Final prerequisite validation | Upgrade Rules page | Passed/warnings accepted | 5–15 min | Gate: SQL setup pass |
| 19 | Ready to upgrade | Confirm settings and capture evidence | Ready to Upgrade page | Correct instance/actions | 5 min | Capture Figure 27 |
| 20 | Start upgrade | Commit engine upgrade | Select Upgrade | Progress begins | 20–180 min | Rollback Point B |
| 21 | Monitor progress | Detect failure promptly | Upgrade Progress page | All components succeed | 20–180 min | Capture Figure 28 |
| 22 | Review completion | Confirm setup status/log links | Complete page | Success for all required components | 5 min | Capture Figure 29 |
| 23 | Reboot only if prompted | Complete component changes | Windows restart | Server returns healthy | 10–30 min | Use console access |
| 24 | Apply approved SQL 2022 CU | Reach enterprise patch baseline | CU installer | Installation successful | 15–60 min | Reboot if prompted |
| 25 | Start/validate SQL services | Restore engine availability | SQL Configuration Manager / services | Services running | 5–15 min | Check error logs |
| 26 | Execute SQL technical validation | Confirm functional state | Queries in Section 24 | Validation passed | 30–90 min | Consider rollback if failure |
| 27 | Re-enable SQL Agent jobs | Resume automation | Apply documented job-state baseline | Correct jobs enabled | 5–15 min | Validate schedules |
| 28 | Execute application tests | Confirm business functionality | App test pack | Passed | 30–120 min | Gate: business acceptance |
| 29 | Update monitoring/backups | Restore normal controls | Monitoring and backup checks | Healthy reports/jobs | 15–60 min | Mandatory |
| 30 | Remove snapshot | End short-term rollback mechanism | vCenter delete/consolidate | Completed | 10–60 min | Only after formal acceptance |
| 31 | Close change | Preserve audit trail | Attach evidence and outcome | Record complete | 15 min | Post-implementation review if needed |

22.3 SQL Setup Screen Figure Register

| Figure | Screen | Engineer Must Verify |
| --- | --- | --- |
| Figure 24 | SQL Server Installation Center | Correct SQL Server 2022 media and Upgrade from a previous version path |
| Figure 25 | Setup Support Rules | No failed prerequisite; warnings assessed and approved |
| Figure 26 | Instance Selection | Exact default/named instance selected; no incorrect instance action |
| Figure 27 | Feature / Upgrade Rules | Required components pass; excluded feature impacts understood |
| Figure 28 | Ready to Upgrade | Target instance, edition, features, directories, service settings are correct |
| Figure 29 | Upgrade Progress | All required components show success |
| Figure 30 | Complete | Setup completed; log location captured |
| Figure 31 | SSMS after upgrade | SQL Server 2022 version, instance availability |
| Figure 32 | SQL Server Properties | Edition, product version, collation, memory configuration |
| Figure 33 | Database compatibility settings | Existing compatibility level retained initially |
| Figure 34 | SQL Agent Jobs | Jobs enabled state and recent execution history |
| Figure 35 | Query Store | Enabled/configured according to approved design |
| Figure 36 | Always On Availability Groups | Replica health/synchronization state, if applicable |

22.4 SQL Setup Logs

Capture and retain the SQL Setup Bootstrap logs, normally under a path similar to:

C:\Program Files\Microsoft SQL Server\160\Setup Bootstrap\Log\

Key artefacts include:

- Summary.txt

- Detail.txt

- Component-specific logs

- Setup rule reports

- Windows Application and System Event Logs

- SQL Server ERRORLOG files

Important: Do not delete setup logs after a successful upgrade. Attach relevant extracts and the summary log to the change record and retain according to the organization’s evidence-retention policy.

23.0 High-Availability and Feature-Specific Scenarios

23.1 SQL Always On Availability Groups

| Requirement | Procedure Direction |
| --- | --- |
| AG assessment | Document replicas, synchronization mode, failover mode, listeners, databases, endpoint ports, quorum, and application connection strings |
| Upgrade model | Use a rolling, replica-by-replica procedure; do not in-place upgrade all replicas simultaneously |
| Sequence | Upgrade secondary replica, validate, fail over in controlled manner, upgrade former primary, validate failback as required |
| Compatibility level | Keep database compatibility level unchanged during platform upgrade |
| Validation | Confirm synchronization health, listener connection, backup preference, failover readiness, and application connectivity |
| Rollback | Retain a supported replica or restore to planned prior state; use topology-specific approved plan |

Warning: An Availability Group’s operating system and SQL version sequence must be designed separately from the generic standalone-instance procedure. The DBA lead must produce the replica-specific execution order and failover decision gates.

23.2 Failover Cluster Instance

| Scenario | Requirement |
| --- | --- |
| Windows Server cluster | Direct 2016-to-2022 cluster rolling upgrade is not supported; cluster rolling upgrades are one release at a time. |
| SQL FCI | Use a combined Windows Failover Cluster and SQL FCI upgrade/migration plan |
| Preferred approach | Build or migrate to a new supported cluster where practical |
| Required approval | Windows Cluster SME, DBA Lead, VMware/Storage Team, Application Owner, CAB |

23.3 Replication, Log Shipping, Mirroring

| Feature | Required Control |
| --- | --- |
| Transactional/merge replication | Capture topology and use Microsoft-supported replication upgrade sequencing |
| Log shipping | Confirm primary/secondary backup-copy-restore chain and monitor jobs |
| Database mirroring | Document endpoint and partner state; assess modernization path |
| Linked servers | Test provider compatibility, connectivity, authentication, and distributed queries |
| SSIS | Back up SSISDB/catalog and validate package execution |
| SSRS | Confirm architecture; Reporting Services may require a separate upgrade/migration procedure |
| SSAS | Validate model compatibility, processing, service accounts, and client connectivity |

24.0 SQL Post-Upgrade Tasks

24.1 Core SQL Validation

-- Validate upgraded SQL Server engine
SELECT @@VERSION AS SqlVersion;
SELECT
    SERVERPROPERTY('Edition') AS Edition,
    SERVERPROPERTY('ProductVersion') AS ProductVersion,
    SERVERPROPERTY('ProductUpdateLevel') AS ProductUpdateLevel,
    SERVERPROPERTY('ProductUpdateReference') AS ProductUpdateReference,
    SERVERPROPERTY('Collation') AS ServerCollation;
GO

-- Database state and compatibility
SELECT
    name,
    state_desc,
    recovery_model_desc,
    compatibility_level,
    is_encrypted,
    log_reuse_wait_desc
FROM sys.databases
ORDER BY name;
GO

-- SQL service health
SELECT
    servicename,
    status_desc,
    startup_type_desc,
    service_account,
    last_startup_time
FROM sys.dm_server_services;
GO

-- Failed SQL Agent jobs since upgrade start
SELECT TOP (100)
    j.name AS JobName,
    h.run_date,
    h.run_time,
    h.run_duration,
    h.run_status,
    h.message
FROM msdb.dbo.sysjobhistory AS h
JOIN msdb.dbo.sysjobs AS j
    ON h.job_id = j.job_id
WHERE h.step_id = 0
ORDER BY h.instance_id DESC;
GO

24.2 Database Compatibility-Level Management

| Stage | Action | Approval Requirement |
| --- | --- | --- |
| Immediately after engine upgrade | Retain existing database compatibility levels | DBA Lead |
| Functional validation | Validate application functions, SQL Agent jobs, integrations, reports, ETL, replication, and HA | Application Owner + DBA |
| Performance baseline | Compare query duration, CPU, waits, I/O, blocking, and error rates | DBA |
| Query Store review | Identify plan regressions after controlled compatibility-level change | DBA |
| Raise compatibility level | Execute per database in approved batches | Separate change or approved sub-task |
| Post-change monitoring | Monitor key workload for agreed period | DBA + Application Owner |

Example after approval:

ALTER DATABASE [DatabaseName] SET COMPATIBILITY_LEVEL = 160;
GO

Warning: Never mass-change all production databases to compatibility level 160 without workload validation and a documented rollback approach.

24.3 Query Store

SELECT
    name,
    desired_state_desc,
    actual_state_desc,
    readonly_reason,
    current_storage_size_mb,
    max_storage_size_mb,
    interval_length_minutes,
    query_capture_mode_desc,
    size_based_cleanup_mode_desc
FROM sys.database_query_store_options;
GO

For each critical database, determine whether Query Store should be enabled, sized, and configured according to the DBA standard before changing database compatibility level.

24.4 Statistics and Integrity

-- Per database, after workload and maintenance-window approval
EXEC sp_updatestats;
GO

-- Execute per database according to maintenance policy
DBCC CHECKDB (N'[DatabaseName]') WITH NO_INFOMSGS, ALL_ERRORMSGS;
GO

24.5 SQL Configuration Validation

SELECT
    name,
    value,
    value_in_use
FROM sys.configurations
WHERE name IN
(
    'max server memory (MB)',
    'min server memory (MB)',
    'max degree of parallelism',
    'cost threshold for parallelism',
    'backup compression default',
    'optimize for ad hoc workloads'
)
ORDER BY name;
GO

24.6 Post-Upgrade Checklist

| Activity | Expected Result | Pass / Fail | Evidence |
| --- | --- | --- | --- |
| SQL version | SQL Server 2022 build and approved CU | [ ] | [Path] |
| SQL services | Database Engine/Agent and required services running | [ ] | [Path] |
| Database state | Required databases online | [ ] | [Path] |
| Compatibility levels | Retained or changed only as approved | [ ] | [Path] |
| DBCC CHECKDB | No consistency errors | [ ] | [Path] |
| SQL Agent jobs | Enabled and successful | [ ] | [Path] |
| Backups | Full/log jobs succeed | [ ] | [Path] |
| Linked servers | Test connection succeeds | [ ] | [Path] |
| Database Mail | Approved test email succeeds | [ ] | [Path] |
| Replication/log shipping/AG | Healthy status | [ ] | [Path] |
| TDE/encryption | Encryption/key access working | [ ] | [Path] |
| SPNs/Kerberos | Expected SPNs and auth behavior | [ ] | [Path] |
| Monitoring | SQL health/metrics/logs visible | [ ] | [Path] |
| Performance | Within approved tolerance | [ ] | [Path] |
| Application validation | Business test pack successful | [ ] | [Path] |

25.0 SQL Validation Test Pack

| ID | Test | Query / Test | Expected Result | Pass / Fail | Owner |
| --- | --- | --- | --- | --- | --- |
| S-01 | Engine version | SELECT @@VERSION | SQL Server 2022 and approved CU | [ ] | DBA |
| S-02 | Edition | SERVERPROPERTY('Edition') | Licensed target edition | [ ] | DBA |
| S-03 | Database status | sys.databases query | Required DBs online | [ ] | DBA |
| S-04 | Database accessibility | Application connection test | Successful login/query | [ ] | App Owner |
| S-05 | Integrity | DBCC CHECKDB | No errors | [ ] | DBA |
| S-06 | SQL Agent | Test approved critical job | Successful completion | [ ] | DBA |
| S-07 | Backup | Trigger/verify backup job | Success | [ ] | Backup/DBA |
| S-08 | Linked server | EXEC sp_testlinkedserver | Success | [ ] | DBA |
| S-09 | Mail | Test DB Mail | Test email delivered | [ ] | DBA |
| S-10 | TDE | Backup/restore or encryption check | Key/certificate available | [ ] | DBA |
| S-11 | Monitoring | Dashboard/service check | SQL availability/metrics present | [ ] | Monitoring |
| S-12 | Performance | Compare baseline workload | Within accepted tolerance | [ ] | DBA |
| S-13 | HA/DR | AG/log shipping/replication validation | Healthy | [ ] | DBA |
| S-14 | Security | Service accounts/SPNs/permissions | Correct and compliant | [ ] | DBA/Security |
| S-15 | Business | End-to-end app transaction | Passed | [ ] | App Owner |

Part III — Rollback and Recovery

26.0 Rollback Principles

Rollback must be initiated when:

- Windows Setup fails and the server cannot return to a stable, supportable operating state.

- SQL Setup fails and remediation cannot restore service within the approved outage.

- Critical application tests fail without an approved workaround.

- Core security controls, backup, monitoring, network connectivity, authentication, encryption, or HA cannot be restored.

- The defined backout deadline is reached without meeting success criteria.

- Technical lead, application owner, or change authority declares a service-risk condition.

26.1 Rollback Decision Matrix

| Condition | Severity | Decision | Recovery Method | Authority |
| --- | --- | --- | --- | --- |
| Setup compatibility blocker | High | Do not proceed | Exit setup; no rollback required | Windows/DBA Lead |
| Windows upgrade fails before boot | Critical | Roll back | VMware snapshot / VM restore | Windows + VMware Lead |
| Windows boots but critical services fail | Critical | Assess within backout window | Remediate or restore snapshot | Technical Lead |
| SQL upgrade fails during setup | Critical | Roll back | Snapshot/VM restore; SQL restore if needed | DBA + VMware Lead |
| SQL starts but databases inaccessible | Critical | Roll back | Restore certificates/keys, then DB/VM recovery | DBA Lead |
| App test fails but infrastructure is stable | High | Assess | Fix within threshold or roll back | App Owner + Tech Lead |
| Monitoring/backup not restored | High | Do not close change | Remediate; roll back if prolonged risk | Security/Operations |
| Performance degradation | Medium/High | Assess against SLA | Tune or revert to prior state | DBA + App Owner |
| Backout deadline reached | Critical | Roll back | Approved rollback plan | Change Manager |

26.2 VMware Snapshot Restore Procedure

| Step | Activity | Expected Result |
| --- | --- | --- |
| 1 | Declare rollback on bridge and record time | All stakeholders informed |
| 2 | Stop application/SQL activity | No active transactions where possible |
| 3 | Confirm snapshot identity and timestamp | Correct pre-change snapshot identified |
| 4 | Use vCenter console to revert to snapshot | VM reverts to pre-upgrade state |
| 5 | Power on VM if required | Server boots |
| 6 | Validate OS, network, AD, SQL, application services | Pre-change service restored |
| 7 | Validate database consistency and transaction exposure | RPO impact recorded |
| 8 | Confirm monitoring, AV/EDR, backup | Controls restored |
| 9 | Obtain application-owner confirmation | Business service operational |
| 10 | Preserve logs and update incident/change record | Evidence retained |

Warning: A snapshot rollback reverts disks to the snapshot point. Assess data loss, external transactions, replication state, backup-chain implications, and application consistency before executing it.

26.3 SQL Restore Procedure

Use when VM rollback is unsuitable or when recovery must be database-specific.

- Stop application services and prevent new transactions.

- Confirm the latest validated full backup, differential backup, and transaction-log chain.

- Restore master, msdb, and user databases only under an approved, instance-specific recovery plan.

- Restore TDE certificates and keys before restoring encrypted databases.

- Restore logins with matching SIDs, jobs, linked servers, credentials, and SQL Agent configuration.

- Validate DBCC, application connectivity, SQL Agent jobs, backups, and monitoring.

- Record achieved RPO/RTO and all recovery actions.

26.4 Rollback Validation

| Test | Expected Result |
| --- | --- |
| OS version | Windows Server 2016 restored where VM rollback used |
| SQL version | SQL Server 2016 restored where VM rollback used |
| Database state | Required databases online |
| Authentication | Domain/service accounts authenticate |
| Application | Critical transaction test succeeds |
| Monitoring | Host and SQL telemetry restored |
| Backup | Next backup job succeeds |
| Security | AV/EDR, firewall, certificates, and logs operational |
| DR | Replication/log shipping/AG health restored as designed |

Part IV — Troubleshooting Guide

27.0 Common Issues

| # | Issue / Symptoms | Likely Cause | Resolution | Commands / Logs |
| --- | --- | --- | --- | --- |
| 1 | Windows Setup blocks upgrade | Unsupported edition/language/install type | Validate source/target matrix; use correct media | Setup compatibility report |
| 2 | “Keep files, settings, and apps” unavailable | Booted from ISO or unsupported path | Launch setup.exe from running Windows 2016 | Setup UI/logs |
| 3 | Setup fails due to disk space | Insufficient OS disk free space | Free/extend C:, clean temp files | Get-Volume, cleanmgr |
| 4 | Pending reboot blocks SQL setup | Windows updates/install pending | Restart server, re-run checks | Registry reboot checks |
| 5 | NIC Teaming warning/failure | Teaming enabled | Disable teaming before upgrade; re-enable afterward | NIC Teaming console |
| 6 | Network unavailable after OS upgrade | VMware Tools/NIC driver issue | Use vCenter console; repair/update VMware Tools; verify NIC config | Device Manager, ipconfig /all |
| 7 | VM fails to boot after upgrade | Setup/driver/boot issue | Review setup logs; restore snapshot if needed | setupact.log, setuperr.log |
| 8 | Server stuck in upgrade loop | Setup failure or insufficient resources | Use console; inspect logs; initiate rollback if not recoverable | Panther logs |
| 9 | RDP unavailable after upgrade | Firewall/NLA/service issue | Validate TermService, firewall rule, DNS, network profile | Test-NetConnection, Event Viewer |
| 10 | Domain trust failure | Secure-channel or time issue | Repair secure channel; validate DNS/time | Test-ComputerSecureChannel, w32tm |
| 11 | Kerberos authentication failures | SPN/service-account issue | Validate/register correct SPNs; avoid duplicates | setspn -Q, setspn -L |
| 12 | GPO not applied | DNS/connectivity/sysvol issue | gpupdate /force; validate DC reachability | gpresult /h, Event Viewer |
| 13 | Services fail after OS upgrade | Dependency, account, or .NET issue | Compare services baseline; inspect service logs | Get-Service, Event Viewer |
| 14 | Scheduled task fails | Credential/compatibility change | Re-enter credentials if approved; validate task history | Task Scheduler |
| 15 | AV/EDR agent unhealthy | Unsupported old agent/filter driver | Upgrade/reinstall supported agent | Vendor logs/console |
| 16 | Backup agent fails | VSS/agent compatibility issue | Update/reinstall agent; test backup | VSS logs, backup console |
| 17 | Monitoring absent | Agent stopped/config lost | Start/reconfigure agent; verify firewall/proxy | Agent logs, dashboard |
| 18 | Event log flood after upgrade | New driver/service warnings | Triage critical events; document known benign events | Get-WinEvent |
| 19 | Windows activation fails | KMS/DNS/network/key issue | Verify KMS access/key/edition | slmgr /dlv, DNS |
| 20 | VMware Tools not running | Tools service/installer issue | Repair/reinstall approved VMware Tools | vCenter, services |
| 21 | SQL Setup Support Rule fails | Pending reboot, .NET, permissions, feature incompatibility | Correct failed rule; rerun setup | Setup Summary.txt, Detail.txt |
| 22 | Wrong SQL instance selected | Multiple instances | Cancel before upgrade; verify instance inventory | SQL services, registry |
| 23 | SQL Setup fails at upgrade rules | Feature/configuration blocker | Review exact rule and feature documentation | Setup logs |
| 24 | SQL service will not start | Account, startup parameter, port, master DB issue | Inspect ERRORLOG; validate account, paths, parameters | SQL ERRORLOG, Event Viewer |
| 25 | SQL Agent does not start | Agent account/configuration issue | Validate service account, permissions, msdb health | SQL Agent log |
| 26 | User database is suspect/recovery pending | Storage or log/data issue | Follow approved recovery; do not force repair without approval | SQL ERRORLOG, sys.databases |
| 27 | DBCC CHECKDB errors | Existing or post-change corruption | Restore from clean backup or follow DBA escalation | DBCC CHECKDB output |
| 28 | TDE database cannot restore/open | Missing certificate/private key | Restore certificate/key securely in master | sys.certificates, restore logs |
| 29 | Application login failure | SID mismatch or auth mode issue | Restore/sync logins with SIDs; validate auth | sys.server_principals |
| 30 | Linked server fails | Provider/driver/TLS/authentication issue | Update supported provider; re-test security mapping | sp_testlinkedserver |
| 31 | Database Mail fails | SMTP TLS/relay config change | Test host/port/TLS; review Database Mail log | sysmail_event_log |
| 32 | SQL Agent job fails | Path, proxy, permissions, changed runtime | Review job history; test manually | msdb..sysjobhistory |
| 33 | SSIS package failures | SSISDB/package/runtime dependency | Validate catalog, protection level, drivers | SSISDB reports/logs |
| 34 | SSRS reports unavailable | Separate SSRS component/config issue | Restore/report-server configuration and test URLs | SSRS logs/config |
| 35 | AG replica unhealthy | Upgrade order, endpoint, version, network issue | Follow AG-specific rolling-upgrade plan | AG dashboard/DMVs |
| 36 | Log shipping jobs fail | Job paths/agent/config issue | Validate share, job ownership, backup chain | msdb log-shipping tables |
| 37 | Replication latency/errors | Agent/version/connectivity issue | Validate distributor/publisher/subscriber sequence | Replication Monitor |
| 38 | SQL port changed/unreachable | Dynamic port/config/firewall issue | Confirm listening port and firewall rules | SQL ERRORLOG, Test-NetConnection |
| 39 | High CPU after upgrade | Plan regression/config shift | Review Query Store, waits, MAXDOP | Query Store/DMVs |
| 40 | Slow queries after compatibility-level increase | Cardinality/plan change | Use Query Store; force approved plan or revert compatibility level | Query Store |
| 41 | Excessive tempdb contention | File layout/config not optimal | Review tempdb file count/size/growth | tempdb.sys.database_files |
| 42 | SQL memory pressure | max server memory not right for host | Recalculate per server reserve standard | PerfMon, sys.configurations |
| 43 | Backup duration increased | I/O, compression, agent, encryption | Compare baseline; validate backup target | Backup history/PerfMon |
| 44 | Instant File Initialization unavailable | Service account lost required privilege | Regrant approved “Perform volume maintenance tasks” right | Local Security Policy |
| 45 | TLS connectivity errors | Legacy client/protocol/cipher mismatch | Update client drivers and TLS configuration per policy | Schannel/SQL logs |
| 46 | Certificate binding failure | Expired/missing certificate or permissions | Validate certificate store/private-key ACLs | MMC certificates, event logs |
| 47 | Windows Update fails post-upgrade | WSUS/MECM component/config issue | Repair policy/connectivity; remediate update agent | WindowsUpdate log/events |
| 48 | Disk snapshot consolidation issue | Snapshot growth/datastore capacity | Work with VMware team; ensure capacity | vCenter tasks/events |
| 49 | SQL setup media mismatch | Wrong edition/build/architecture | Use approved SQL 2022 x64 media | Setup metadata |
| 50 | Unexpected reboot during setup | Patch policy/watchdog/automation | Prevent maintenance automation during window | Task Scheduler, patch tooling |
| 51 | Setup cannot access media | ISO disconnected/permissions issue | Reconnect ISO; copy media to approved local path | vCenter/Setup log |
| 52 | SQL browser/client connectivity issue | SQL Browser/service/firewall configuration | Validate Browser, static/dynamic ports, aliases | SQL Config Manager |
| 53 | Cluster validation errors | Unsupported direct cluster OS path | Use one-version rolling upgrade or migration | Cluster validation report |
| 54 | HSM/EKM key access failure | Provider/credential incompatibility | Validate vendor support, provider registration, credentials | SQL ERRORLOG/vendor logs |
| 55 | Audit logging stops | SQL audit/agent/config issue | Validate audit target path, permissions, SIEM ingestion | SQL audit logs/Splunk |
| 56 | Splunk forwarding stops | Universal Forwarder service/config issue | Start/reconfigure forwarder, verify TLS/connectivity | Forwarder logs |
| 57 | SolarWinds/SCOM alert storm | Baselines/agent reboot state | Maintenance mode, then validate normal telemetry | Monitoring console |
| 58 | Application uses deprecated SQL behavior | SQL engine or driver compatibility | Remediate application/driver; retain DB compatibility temporarily | App logs/Query Store |
| 59 | Login uses obsolete ODBC/OLE DB provider | Client driver incompatibility | Deploy approved Microsoft driver and regression test | App/server logs |
| 60 | Rollback fails to meet RTO | Unrehearsed restore or capacity issue | Invoke DR plan, escalate incident, capture lessons learned | Backup/VMware records |

Important: The Microsoft references in Section 8.0 are the authoritative starting point for supported upgrade paths and requirements. Apply current product documentation and approved vendor support matrices before every production execution.

Part V — Architecture Diagrams

28.0 Existing Environment

flowchart LR
    U[Business Users / Applications] --> LB[Load Balancer or DNS Alias]
    LB --> APP[Application Servers]
    APP --> SQL[SQL Server 2016 on Windows Server 2016]
    SQL --> DB[(User Databases)]
    SQL --> BAK[Enterprise Backup Platform]
    SQL --> MON[SCOM / SolarWinds / Splunk]
    SQL --> AD[Active Directory / DNS / PKI]
    SQL --> VMW[VMware vCenter / ESXi]
    SQL --> SEC[AV / EDR / PAM / Vulnerability Scanning]

29.0 Upgrade Workflow

flowchart TD
    A[Approve Change and Outage] --> B[Complete Compatibility Assessment]
    B --> C[Validate Backup and Restore Test]
    C --> D[Capture Pre-Upgrade Evidence]
    D --> E[Stop Application and SQL Workload]
    E --> F[Create VMware Snapshot]
    F --> G[Upgrade SQL Server 2016 to 2022]
    G --> H[Validate SQL and Application]
    H --> I[Upgrade Windows Server 2016 to 2022]
    I --> J[Validate OS, Agents, Network, Security]
    J --> K[Business Validation]
    K --> L[Remove Snapshot and Close Change]

30.0 Decision Tree

flowchart TD
    A[Start Assessment] --> B{Standalone non-clustered server?}
    B -- No --> C[Use cluster or migration-specific procedure]
    B -- Yes --> D{Windows 2016 to 2022 path valid?}
    D -- No --> E[Use migration / rebuild]
    D -- Yes --> F{Apps, agents, drivers supported?}
    F -- No --> E
    F -- Yes --> G{Backup and restore test successful?}
    G -- No --> H[Do not proceed]
    G -- Yes --> I{SQL feature / HA plan approved?}
    I -- No --> H
    I -- Yes --> J[Proceed with scheduled upgrade]

31.0 Rollback Workflow

flowchart TD
    A[Failure or Success Criteria Not Met] --> B{Within Backout Window?}
    B -- Yes --> C[Declare Rollback]
    B -- No --> D[Escalate to Major Incident / DR Decision]
    C --> E{VM Snapshot Appropriate?}
    E -- Yes --> F[Restore Snapshot]
    E -- No --> G[Restore SQL / VM Backup]
    F --> H[Validate OS, SQL, Application, Security, Monitoring]
    G --> H
    H --> I[Confirm Business Recovery]
    I --> J[Update Change and Incident Records]

32.0 Backup and Recovery Flow

flowchart LR
    SQL[SQL Server] --> F[Full Database Backup]
    SQL --> D[Differential Backup]
    SQL --> T[Transaction Log Backup]
    SQL --> S[System Database Backup]
    SQL --> K[TDE Certificates / Keys / Config Exports]
    F --> R[Protected Backup Repository]
    D --> R
    T --> R
    S --> R
    K --> V[Approved Secrets Vault / Encrypted Escrow]
    R --> X[Restore Test Environment]
    X --> Y[Recovery Validation Evidence]

33.0 Service Dependency Map

flowchart TD
    AD[AD DS / DNS / PKI / NTP] --> WIN[Windows Server 2022]
    VMW[VMware Platform] --> WIN
    WIN --> SQL[SQL Server 2022 Services]
    SEC[AV/EDR/PAM] --> WIN
    MON[Monitoring / SIEM] --> WIN
    BAK[Backup Agent] --> WIN
    SQL --> APP[Application Services]
    SQL --> INT[Linked Servers / ETL / Reporting / SMTP]
    APP --> USER[Business Users]

Part VI — Change Management Package

34.0 Implementation Plan

| Phase | Activity | Owner | Start | End | Completion Evidence |
| --- | --- | --- | --- | --- | --- |
| Planning | Assessment, compatibility, risk review | Windows/DBA | [Time] | [Time] | Assessment report |
| Readiness | Backup and restore validation | Backup/DBA | [Time] | [Time] | Backup job/restore report |
| Pre-change | Notifications, bridge, maintenance mode | Change Manager | [Time] | [Time] | Communications |
| Execution | SQL upgrade | DBA | [Time] | [Time] | Setup logs/validation |
| Execution | Windows upgrade | Windows Team | [Time] | [Time] | Setup logs/validation |
| Validation | Technical checks | All technical teams | [Time] | [Time] | Validation checklist |
| Validation | Business testing | Application Owner | [Time] | [Time] | Business sign-off |
| Closure | Snapshot deletion, documentation | VMware/Change Manager | [Time] | [Time] | Change closure record |

35.0 Impact Analysis

| Domain | Expected Impact | Mitigation |
| --- | --- | --- |
| Application availability | Planned outage/interruption | Approved maintenance window and user communications |
| Database connectivity | SQL unavailable during engine restart/upgrade | Stop transactions; application maintenance mode |
| Monitoring | Temporary alerts/telemetry gap | Maintenance mode and post-change validation |
| Backup | Backup schedule may be paused | Coordinate job suspension/resumption |
| Security | Temporary agent/service interruption if approved | Security approval and validation before closure |
| DR | Replication/AG/log shipping may require coordinated pause | DBA/DR topology plan |
| Network | Possible brief NIC/service restart | Console access and network team standby |
| Compliance | High-risk change requires evidence | Capture logs, screenshots, approvals, validation results |

36.0 Communication Plan

| Audience | Timing | Channel | Message Owner |
| --- | --- | --- | --- |
| CAB | Before implementation | CAB record | Change Manager |
| Application owner | Before, during, after | Email/bridge | Change Manager |
| Service desk | Before outage | Incident/change notification | Operations |
| Business users | Before outage and completion | Approved business channel | Application Owner |
| Security/SOC | Before and after | Ticket/bridge | Security Lead |
| Backup/DR | Before and after | Ticket/bridge | Infrastructure Lead |
| Management | Start, major issue, completion | Status update | Change Manager |

37.0 Success Criteria

The change is successful only when all of the following are met:

- Windows Server reports Windows Server 2022 and is activated.

- SQL Server reports SQL Server 2022 with the approved cumulative update.

- All required SQL services and Windows services are running.

- All required databases are online and pass agreed integrity checks.

- Backups complete successfully after upgrade.

- Monitoring, SIEM/log forwarding, AV/EDR, and vulnerability/security controls are healthy.

- Network, DNS, AD authentication, certificates, SPNs, and firewall controls work as designed.

- Application owner completes and approves end-to-end business validation.

- HA/DR controls are healthy where applicable.

- No unresolved Severity 1/2 defects exist.

- Evidence is attached to the change record.

38.0 CAB Checklist

| Check | Status |
| --- | --- |
| Business justification and end-of-support risk documented | [ ] |
| Upgrade path confirmed as supported | [ ] |
| Application and vendor compatibility approved | [ ] |
| Licensing validated | [ ] |
| Backup and restore test complete | [ ] |
| VM snapshot capacity validated | [ ] |
| SQL topology and feature assessment complete | [ ] |
| Security/AV/EDR approval received | [ ] |
| Monitoring and backup agent compatibility confirmed | [ ] |
| Downtime approved | [ ] |
| Communications approved | [ ] |
| Detailed rollback plan reviewed | [ ] |
| Technical resources and escalation contacts confirmed | [ ] |
| Business validation script accepted | [ ] |
| Evidence-retention requirements defined | [ ] |

Part VII — Printable Operational Checklists

39.0 Pre-Upgrade Checklist

| Item | Completed | Owner | Evidence |
| --- | --- | --- | --- |
| Correct server/instance identified | [ ] | [ ] | [ ] |
| CAB approval obtained | [ ] | [ ] | [ ] |
| Downtime approved | [ ] | [ ] | [ ] |
| Upgrade media hash validated | [ ] | [ ] | [ ] |
| Licensing confirmed | [ ] | [ ] | [ ] |
| Application support confirmed | [ ] | [ ] | [ ] |
| VMware compatibility confirmed | [ ] | [ ] | [ ] |
| Roles/features inventory captured | [ ] | [ ] | [ ] |
| Agent compatibility confirmed | [ ] | [ ] | [ ] |
| No pending reboot | [ ] | [ ] | [ ] |
| Disk capacity sufficient | [ ] | [ ] | [ ] |
| Pre-upgrade performance baseline captured | [ ] | [ ] | [ ] |
| SQL assessment complete | [ ] | [ ] | [ ] |
| DBCC CHECKDB clean | [ ] | [ ] | [ ] |
| HA/DR assessment complete | [ ] | [ ] | [ ] |
| Business validation plan ready | [ ] | [ ] | [ ] |

40.0 Backup Checklist

| Item | Completed | Owner | Evidence |
| --- | --- | --- | --- |
| VM backup completed successfully | [ ] | [ ] | [ ] |
| VM restore evidence reviewed | [ ] | [ ] | [ ] |
| VMware snapshot capacity confirmed | [ ] | [ ] | [ ] |
| Full user DB backups completed | [ ] | [ ] | [ ] |
| System DB backups completed | [ ] | [ ] | [ ] |
| Transaction-log/tail-log backup completed if applicable | [ ] | [ ] | [ ] |
| TDE certificates/keys secured | [ ] | [ ] | [ ] |
| SQL Agent jobs exported | [ ] | [ ] | [ ] |
| Logins/SIDs exported | [ ] | [ ] | [ ] |
| Linked servers/configuration scripted | [ ] | [ ] | [ ] |
| Restore test completed | [ ] | [ ] | [ ] |

41.0 Implementation Checklist

| Item | Completed | Owner | Evidence |
| --- | --- | --- | --- |
| Change bridge started | [ ] | [ ] | [ ] |
| Stakeholders notified | [ ] | [ ] | [ ] |
| Final backup validation completed | [ ] | [ ] | [ ] |
| Application stopped/maintenance enabled | [ ] | [ ] | [ ] |
| Monitoring maintenance mode enabled | [ ] | [ ] | [ ] |
| SQL Agent jobs disabled | [ ] | [ ] | [ ] |
| VMware snapshot created | [ ] | [ ] | [ ] |
| SQL upgrade completed | [ ] | [ ] | [ ] |
| SQL CU applied | [ ] | [ ] | [ ] |
| Windows upgrade completed | [ ] | [ ] | [ ] |
| OS updates applied as approved | [ ] | [ ] | [ ] |
| Agents re-enabled/validated | [ ] | [ ] | [ ] |

42.0 Validation Checklist

| Item | Completed | Owner | Evidence |
| --- | --- | --- | --- |
| Windows Server 2022 version verified | [ ] | [ ] | [ ] |
| Windows activation verified | [ ] | [ ] | [ ] |
| SQL Server 2022 version verified | [ ] | [ ] | [ ] |
| SQL databases online | [ ] | [ ] | [ ] |
| SQL Agent jobs validated | [ ] | [ ] | [ ] |
| Backup job succeeded | [ ] | [ ] | [ ] |
| Monitoring healthy | [ ] | [ ] | [ ] |
| SIEM logging received | [ ] | [ ] | [ ] |
| AV/EDR healthy | [ ] | [ ] | [ ] |
| DNS/network/firewall validated | [ ] | [ ] | [ ] |
| AD/Kerberos/SPNs validated | [ ] | [ ] | [ ] |
| HA/DR validated | [ ] | [ ] | [ ] |
| Business validation passed | [ ] | [ ] | [ ] |
| Snapshot removed after acceptance | [ ] | [ ] | [ ] |

43.0 Rollback Checklist

| Item | Completed | Owner | Evidence |
| --- | --- | --- | --- |
| Rollback decision authorized | [ ] | [ ] | [ ] |
| Stakeholders notified | [ ] | [ ] | [ ] |
| Application transactions stopped | [ ] | [ ] | [ ] |
| Correct snapshot/backup identified | [ ] | [ ] | [ ] |
| Snapshot or restore initiated | [ ] | [ ] | [ ] |
| OS/SQL restored | [ ] | [ ] | [ ] |
| Application validated | [ ] | [ ] | [ ] |
| Monitoring/security/backup restored | [ ] | [ ] | [ ] |
| RPO/RTO recorded | [ ] | [ ] | [ ] |
| Incident/change updated | [ ] | [ ] | [ ] |

44.0 Sign-Off Checklist

| Role | Sign-Off | Date | Notes |
| --- | --- | --- | --- |
| Windows Lead | [ ] | [ ] | [ ] |
| DBA Lead | [ ] | [ ] | [ ] |
| VMware Lead | [ ] | [ ] | [ ] |
| Backup Lead | [ ] | [ ] | [ ] |
| Security Lead | [ ] | [ ] | [ ] |
| Monitoring Lead | [ ] | [ ] | [ ] |
| Application Owner | [ ] | [ ] | [ ] |
| Change Manager | [ ] | [ ] | [ ] |

Appendices

Appendix A — PowerShell Command Reference

# OS version and baseline
Get-ComputerInfo
systeminfo
winver

# Network
Get-NetIPAddress -AddressFamily IPv4
Get-DnsClientServerAddress -AddressFamily IPv4
Get-NetRoute -DestinationPrefix 0.0.0.0/0
Test-NetConnection [HostName] -Port [Port]
Resolve-DnsName [FQDN]

# Services and tasks
Get-Service | Sort-Object Name
Get-ScheduledTask
Get-ScheduledTaskInfo -TaskName "[TaskName]" -TaskPath "\"

# Roles/features
Get-WindowsFeature | Where-Object Installed

# Applications
Get-ItemProperty HKLM:\Software\Microsoft\Windows\CurrentVersion\Uninstall\*,
                 HKLM:\Software\Wow6432Node\Microsoft\Windows\CurrentVersion\Uninstall\* |
Where-Object DisplayName

# Disks
Get-Volume
Get-Disk
Get-PhysicalDisk

# Security and certificates
manage-bde -status
Get-ChildItem Cert:\LocalMachine\My
Get-NetFirewallRule
Get-SmbServerConfiguration

# AD/GPO/time
Test-ComputerSecureChannel -Verbose
gpupdate /force
gpresult /h C:\UpgradeEvidence\GPResult.html
w32tm /query /status
w32tm /query /source

# Events
Get-WinEvent -LogName System -MaxEvents 200
Get-WinEvent -LogName Application -MaxEvents 200

# Activation
slmgr /xpr
slmgr /dlv

# SPNs
setspn -L [DOMAIN\ServiceAccount]
setspn -Q MSSQLSvc/[ServerFQDN]:[Port]

Appendix B — SQL Query Reference

Use the SQL queries in Sections 19, 20, and 24 for:

- Instance discovery

- Edition/version confirmation

- Database health and compatibility checks

- DBCC integrity validation

- Jobs and schedules

- Linked servers

- Certificates and TDE

- Service accounts and services

- Server configuration

- TempDB

- Query Store

- Wait statistics and active requests

- Database Mail

- HA/DR validation

Appendix C — Registry and Configuration Evidence

| Item | Evidence / Path | Purpose |
| --- | --- | --- |
| SQL instance names | HKLM\SOFTWARE\Microsoft\Microsoft SQL Server\Instance Names\SQL | Identify default/named instances |
| SQL startup parameters | SQL Server Configuration Manager / service registry | Confirm master/errorlog/tempdb parameters |
| Windows services | HKLM\SYSTEM\CurrentControlSet\Services | Capture service configuration where needed |
| Pending reboot | CBS, Windows Update, Session Manager registry keys | Detect restart requirement |
| Firewall configuration | Windows Defender Firewall policy/export | Preserve network access controls |
| NIC configuration | Get-NetAdapter, Get-NetIPConfiguration | Preserve networking state |

Warning: Do not make registry changes solely because an upgrade occurred. Apply only approved, documented configuration changes that have passed testing and security review.

Appendix D — Core Service Checklist

| Service Category | Examples | Required State |
| --- | --- | --- |
| Windows core | RPC, Event Log, Task Scheduler, WMI | Running |
| AD-integrated services | Netlogon, DNS Client, Time Service | Running/configured as applicable |
| SQL | Database Engine, SQL Agent, SQL Browser, Full-Text | Per design |
| Security | AV/EDR, vulnerability scanner, PAM agent | Healthy/reporting |
| Monitoring | SCOM/SolarWinds/Splunk/Instana agents | Healthy/reporting |
| Backup | Enterprise backup agent/VSS integration | Healthy |
| Application | [App-specific services] | Running and tested |

Appendix E — Common Port Requirements

| Service | Default Port | Notes |
| --- | --- | --- |
| RDP | TCP 3389 | Restrict to approved admin networks |
| DNS | TCP/UDP 53 | Required for AD/name resolution |
| Kerberos | TCP/UDP 88 | AD authentication |
| LDAP | TCP/UDP 389 | Directory access |
| LDAPS | TCP 636 | Secure directory access |
| SMB | TCP 445 | File shares, backups, cluster dependencies where applicable |
| SQL default instance | TCP 1433 | May be static/dynamic/custom |
| SQL Browser | UDP 1434 | Named instance discovery where used |
| SQL AG endpoint | TCP [Custom] | Validate configured endpoint |
| WinRM | TCP 5985/5986 | Management, if enabled |
| HTTPS | TCP 443 | Monitoring, repositories, application endpoints |
| SMTP | TCP 25/587/custom | Database Mail, if configured |

Best Practice: Do not treat default ports as authoritative. Validate actual configured SQL ports, application flows, firewall policy, and segmentation rules in the specific environment.

Appendix F — Security Hardening Recommendations

- Maintain supported Windows Server and SQL Server CUs according to the organization’s risk-based patch standard.

- Enforce least privilege for local administrators, SQL sysadmin, SQL Agent proxies, service accounts, backup accounts, and monitoring accounts.

- Use managed service accounts or approved non-interactive service identities where applicable.

- Validate SPNs and enforce Kerberos where required by the application design.

- Ensure AV/EDR exclusions follow vendor and internal security guidance; do not use broad exclusions.

- Verify TLS, certificate expiry, cipher/protocol policy, and secure SQL client drivers.

- Enable and forward relevant Windows, SQL Server, SQL Agent, audit, and security logs to the SIEM.

- Ensure backups are encrypted, access controlled, immutable where required, and restore-tested.

- Validate SMB signing/encryption and secure file-share access for backup, log shipping, and HSM/EKM dependencies where applicable.

- Reassess firewall rules and network segmentation after the upgrade; remove obsolete exposures.

- Confirm privileged-access management controls and break-glass access are retained and logged.

- Review local security policy changes after upgrade and reapply approved hardening baselines through GPO/configuration management.

Appendix G — Performance Recommendations

| Area | Recommendation |
| --- | --- |
| SQL memory | Revalidate max server memory so Windows, agents, backup, and security software retain sufficient memory |
| MAXDOP | Review according to CPU topology and internal SQL standards |
| Cost threshold | Validate workload-appropriate threshold rather than retaining a legacy default blindly |
| TempDB | Use consistent file sizes/growth settings; validate storage and contention behavior |
| Data/log files | Pre-size based on workload; use fixed MB growth rather than percentage growth where appropriate |
| IFI | Confirm approved service-account privilege for instant file initialization |
| Query Store | Enable/configure for critical databases before compatibility-level changes |
| Statistics | Update based on approved maintenance policy, workload, and maintenance window |
| Storage | Compare read/write latency, throughput, queue depth, and backup duration with baseline |
| Monitoring | Monitor CPU, memory grants, waits, blocking, deadlocks, I/O latency, log usage, and job failures after cutover |

Appendix H — Evidence Pack Index

| Artefact | Filename / Reference |
| --- | --- |
| Pre-upgrade OS inventory | [Server]_ComputerInfo_Pre.txt |
| Installed features | [Server]_WindowsFeatures_Pre.csv |
| Installed applications | [Server]_InstalledApplications_Pre.csv |
| Driver inventory | [Server]_Drivers_Pre.csv |
| Services/tasks inventory | [Server]_Services_Pre.csv, [Server]_ScheduledTasks_Pre.csv |
| GPO report | [Server]_GPResult_Pre.html |
| Performance baseline | [Server]_PerfBaseline_Pre.blg |
| SQL assessment outputs | [Instance]_SQL_PreAssessment.sql/.csv |
| DBCC results | [Database]_CHECKDB_Pre.txt |
| Backup evidence | [BackupJobID/ConsoleScreenshot] |
| TDE certificate evidence | [VaultReference] |
| VMware snapshot evidence | [SnapshotName/Screenshot] |
| Windows setup logs | [Path/Archive] |
| SQL setup logs | [SetupBootstrapLogArchive] |
| Post-upgrade validation | [Server]_PostValidation.xlsx/.pdf |
| Application sign-off | [ApplicationOwnerApproval] |
| Change closure report | [CHGxxxx Closure Record] |

⁂

- https://learn.microsoft.com/en-us/sql/database-engine/install-windows/supported-version-and-edition-upgrades-2022?view=sql-server-ver17

- https://learn.microsoft.com/en-us/sql/sql-server/install/hardware-and-software-requirements-for-installing-sql-server-2022?view=sql-server-ver17

- https://learn.microsoft.com/en-us/troubleshoot/sql/database-engine/install/windows/use-sql-server-in-windows

- https://www.sqlnethub.com/blog/operating-system-requirements-for-all-sql-server-versions-and-editions/

- https://www.dell.com/support/kbdoc/en-us/000191552/in-place-upgrade-guidelines-for-windows-server-2022

- https://learn.microsoft.com/en-us/answers/questions/5860750/is-direct-in-place-upgrade-possible-from-windows-2

- https://learn.microsoft.com/en-us/sql/database-engine/install-windows/upgrade-downgrade-sql-server-edition-setup?view=sql-server-ver17

- https://learn.microsoft.com/en-us/windows-server/get-started/upgrade-conversion-options

- https://www.ibm.com/support/pages/place-upgrade-or-new-installation-when-upgrading-sql-server

- https://learn.microsoft.com/en-us/windows-server/get-started/install-upgrade-migrate

- https://documentation.commvault.com/2023e/commcell-console/microsoft_sql_server_system_requirements.html

- https://learn.microsoft.com/pl-pl/sql/database-engine/install-windows/supported-version-and-edition-upgrades-2022?view=sql-server-ver17

- https://www.microsoft.com/en-us/download/details.aspx?id=105013

- https://learn.microsoft.com/en-us/sql/database-engine/install-windows/upgrade-sql-server?view=sql-server-ver17

- https://learn.microsoft.com/en-us/troubleshoot/sql/releases/download-and-install-latest-updates